## Sheet1
|  | Item | Responsibility | Status | Saturn Update 2019.01.31 | Government Update 2019.02.11 | Saturn Update 2019.02.19 | Government Update 2019.02.27 | Saturn Update 2019.03.04 | Government Update 2019.03.15 | Saturn Update 2019.03.22 | Government Update 2019.03.29 | Government Update 2019.04.03 | Saturn Update 2019.04.04 | Saturn Update 2019.04.11 | Government Update 2019.04.12 | Government Update 2019.04.18 | Government Update 2019.04.25 | Saturn Update 2019.04.26 | Saturn Update 2019.04.29 | Saturn Update 2019.05.02 | Government Update 2019.05.03 | Saturn Update 2019.05.06 | Government Update 2019.05.09 | Saturn Update 2019.05.13 | Government Update 2019.05.17 | Saturn Update 2019.05.22 | Government Update 2019.05.23 | Saturn Update 2019.05.30 | Saturn Update 2019.06.05 | Government Update 2019.06.06 | Saturn Update 2019.06.019 | Saturn Update 2019.06.027 | Saturn Update 2019.07.04 | Government Update 2019.07.05 | Saturn Update 2019.07.07 | Government Update 2019.07.09 | Saturn Update 2019.07.15 | Government Update 2019.07.19 | Saturn Update 2019.07.26 | Government Update 2019.07.31 | Call Update 2019.08.09 | Call Update 2019.08.16 | Call Update 2019.08.23 | Call Update 2019.08.30 | Call Update 2019.09.06 | Call Update 2019.09.13 | Call Update 2019.09.27 | Call Update 2019.10.04 | Call Update 2019.10.11 | Call Update 2019.10.18 | Call Update 2019.10.25 | Call Update 2019.11.01 | Call Update 2019.11.08 | Call Update 2019.11.15 | Call Update 2019.11.22 | Call Update 2019.11.29 | Call Update 2019.12.06 | Call Update 2019.12.12 | Call Update 2019.12.19 | Call Update 2019.12.27 | Call Update 2020.01.03 | Call Update 2020.01.10 | Call Update 2020.01.17 | Call Update 2020.01.24 | Call Update 2020.01.31 | Call Update 2020.02.07 | Call Update 2020.02.14 | Call Update 2020.02.21 | Call Update 2020.02.28 | Call Update 2020.03.06 | Call Update 2020.03.13 | Call Update 2020.03.20 | Call Update 2020.03.27 | Call Update 2020.04.03 | Call Update 2020.04.17 | Call Update 2020.04.24 | Call Update 2020.05.01 | Call Update 2020.05.08 | Call Update 2020.05.15 | Call Update 2020.05.22 | Call Update 2020.05.28 | Call Update 2020.06.05 | Call Update 2020.06.12 | Call Update 2020.06.19 | Call Update 2020.06.26 | Call Update 2020.07.02 | Call Update 2020.07.10 | Call Update 2020.07.17 | Call Update 2020.07.24 | Call Update 2020.08.07 | Call Update 2020.08.14 | Call Update 2020.08.28 | Call Update 2020.09.04 | Call Update 2020.09.11 | Call Update 2020.09.18 | Call Update 2020.09.25 | Call Update 2020.10.02 | Call Update 2020.10.09 | Call Update 2020.10.16 | Call Update 2020.10.23 | Call Update 2020.10.30 | Call Update 2020.11.06 | Call Update 2020.11.13 | Call Update 2020.11.20 | Call Update 2020.11.27 | Call Update 2020.12.4 | Call Update 2020.12.11 | Call update 2021.01.08 | Call update 2021.01.15 | Call update 2021.01.22 | Call update 2021.01.29 | Call update 2021.02.05 | Call update 2021.02.12 | Call update 2021.02.19 | Call update 2021.02.26 | Call update 2021.03.05 | Call update 2021.03.12 | Call update 2021.03.19 | Call update 2021.03.26 | Call update 2021.04.01 | Call update 2021.04.09 | Call update 2021.04.16 | Call update 2021.04.23 | Call update 2021.04.30 | Call update 2021.05.7 | Call update 2021.05.14 | Call update 2021.05.21 | Call update 2021.06.04 | Call update 2021.06.11 | Call update 2021.06.18 | Call update 2021.06.25 | Call update 2021.07.02 | Call update 2021.07.09 | Call update 2021.07.16 | Call update 2021.07.23 | Call update 2021.08.06 | Call update 2021.08.13 | Call update 2021.08.20 | Call update 2021.08.27 | Sept. 3rd 2021 | Sept. 10th 2021 | Sept. 17th 2021 | Sept. 24th 2021 | Oct. 1st 2021 | Oct. 8th 2021 | Oct. 15th 2021 | Oct. 22nd 2021 | Oct. 30th 2021 | Nov 5th. 2021 | Nov 12th. 2021 | Nov 19th. 2021 | Nov 26th. 2021 | Dec 3rd. 2021 | Dec 14th. 2021
IMPLEMENTATION AGREEMENT
1 | 1 | Annual report to Government re Authorization Applications | Saturn | Saturn to Advise | We have provided in the form of an official letter. | Clause 4.3 of the Implementation Agreement requires copies of any Authorizations which have been obtained to be provided to Government. We have set up a secure data room to facilitate the sharing of all project documents. Once Saturn have been provided with login details we ask that copies of all authorizations be uploaded to the secure data room and Government be notified of these so that they can review them. | Thank You, we look forward to receiving the link to the data room so we can provide you with the authorizations. | A data room has been set up and access was provided to Saturn on 25/02/19. Please upload all the relevant documents to the data room. Website: https://web.tresorit.com/l#WE5ebqvf1FwGMqzDJ41BCw Password: Sol@rEnerg! | We are actively uploading files into the Data Room. Construction Permit and the Operating License/Controlled Plant License/Clean Air License. | Government has reviewed documents in the data room and thanks Saturn for uploading them. | Saturn continues to upload documents. | Government has reviewed documents in the data room and thanks Saturn for uploading them. | Government has reviewed documents in the data room and thanks Saturn for uploading them. | Saturn continues to upload documents. | Saturn continues to upload documents as necessary. | Noted | Noted | Noted | Saturn continues to Upload documents. We have uploaded the document consolidating responses from Skyport, BAA, and BCAA. | Saturn continues to upload documents. When site protocol is ready, Saturn will upload it and notify GOB. | Saturn continues to upload documents. When site protocol is ready, Saturn will upload it and notify GOB. | Noted | GOB is satisfied with uploaded site protocol. Other documents will continue to be uploaded as they become available. | Noted | Noted | Are there any recent Authorizations which need to be uploaded to the Data Room? | No Update | No Update | No Update | Letters of consent to be uploaded | Noted | No Update | Confirmation letter that Revision permit application has been approved by both Planning and Building control uploaded into data room. | No Update | Noted | Nana to receive access to the data room. Revised letter for Advance Works and to Start Construction to be uploaded into the data room. | Nan+AJ3:AL3a given access to Data Room on 08/07/19 | No Update | Nana to get all Data Room documents from Aran as access. | No Change | Nana Any Update? | Aran to provide | Saturn to upload Letter to Minister for Lift and Shift along with Saturn's offer to build the fence. | Saturn to upload Letter to Minister for Lift and Shift along with Saturn's offer to build the fence. | Saturn email sent to Project Team With This Information Contained Within. | Saturn Uploaded to Data Room | Saturn to upload relevant documents again to data room | Saturn to upload relevant documents again to data room | Saturn continues to upload documents to Data Room | Saturn continues to upload documents to Data Room | Saturn continues to upload documents to Data Room | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | Completed | [41 empty] | Complete | Complete | Complete | Complete | Complete | Complete
2 | 2 | Certificate of confirmation of Local Labor Content and supporting documents | Saturn | Saturn to advise | We are requiring our contractors to comply with 50% Bermudian labor. Upon construction we will provide actual payroll documents to confirm compliance. | Noted | We are requiring our contractors to comply with 50% Bermudian labor. Upon construction we will provide actual payroll documents to confirm compliance. | Noted | We are requiring our contractors to comply with 50% Bermudian labor. Upon construction we will provide actual payroll documents to confirm compliance. | Noted. Government awaits for Saturn to send monthly documentation once project construction commences. | Saturn to send monthly documentation when construction begins | Noted | Noted | Saturn to send monthly documentation when construction begins | Saturn to send monthly documentation when construction begins | Noted | Noted | Noted | We will provide when construction begins. | We will provide when construction begins. | We will provide when construction begins. | Noted | Mobilization to occur between May 6th and 10th. Pile-driving to begin between May 16th and 18th. Certificates to be provided after these events commence. | Noted | Reports to be provided on a monthly basis. | Noted | Noted | Noted | Noted | Once construction starts, Saturn will provide reports on a bi-weekly basis | Noted | No Update | Construction has started. Reporting will start shortly. | No Update | Noted | Construction commenced on June 24th. Report will be sent on a monthly basis to Aran. | Noted | No Update | Noted | No Change | Saturn intends submitting local labour content reports to GoB week of August 5th. | Mike to provide reports | Mike to send out June & July's reports | Saturn - to upload to the data room. GoB to review and respond. | Local Labour Content Reports Shared With Minister Roban. MHA has no further comment at this time. | No Update | Saturn to provide August report week of 16th September | Saturn to provide 27th September | GoB received Aug report waiting to receive Sept. report. | GoB received Sept. report. shared with Minister | No update | No update | No update | October local labour report received and uploaded to the data room. | No update | No update | No update | No update | November Local Labour Content Report Recevied by GoB | No update | No update | No update | December Local Labour Content Report Recevied by GoB | No Update | No Update | No Update | No Update | Saturn sent GoB received Jan 2020 report | No update | No update | No update | No update | No update | No update | No update | March 2020 Labour Report reveiced by GoB Team and forwarded to Minister Roban. | No update | Will provide April labour report once receive it from NOESIS | Will provide April labour report once receive it from NOESIS | Saturn to provide April labour report once receive it from NOESIS. | April 2020 Labour Report reveiced by GoB Team and forwarded to Minister Roban. | No Update | No Update | No Update | May 2020 Labour Report reveiced by GoB Team and forwarded to Minister Roban. | No Update | No Update | Awaiting June report from sub-contractor. Saturn to follow up 10/07/20 | GoB requested that June Report be submitted although no work carried out | Saturn - June report to be sent although no work done in the month. | Saturn to send July report once completed. | July 2020 report due | Local labour report for July/August 2020 sent to GoB 28/08/20 | No Update | No Update | No Update | No Update | Saturn to send GoB Sept. 2020 report week of 05/10/20 | Saturn to send GoB Sept. 2020 report week of 09/10/20 | Saturn to send GoB Sept. 2020 report week of 19/10/20 | Gov. received Sept./Oct. 2020 report week of 21/10/20 | No Update | No Update | No Update | No Update | No Update | Saturn to send latest Labour Report week of 7/12/20 | GoB recevied Local Labour Report 10/12/20 | Larry Henry to send updated Labour reports week of 11/01/21 | Saturn Provided 14/01/21 | Saturn Provided 14/01/21 | Saturn Provided 14/01/21 | No Update | Saturn to provide update end of Feb. 2021 | Saturn to provide update end of Feb. 2021 | GoB received Jan/Feb 2021 Report from Saturn 26/02/21 | Saturn will submit annual Local Labor Reports as required under Sect. 4.4.2 of Implementation Agreement. | Saturn sent Annual Certifcation of Local Labour Content draft letter to GOB for comment 11/03/21 | Saturn to send Annual Certifcation of Local Labour Content as PDFs to GoB | Annual reports - Shanna have been sent to MHA by courier. | Original delevered by courier - Govt. to confirm received. | Confirm MHA received. MPW to be sent to SC home address due to Office lockdown under COVID. Labour Report for March 2021 to be sent. | No Upate | No Upate | No Upate | GoB Received April 2021 Update | No Update | No Update | GoB Received May 2021 Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | GoB/Sturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | GoB/Saturn agreed that the final LLC reports could be submitted all at the same time once the project has been commissioned. | No change from last week. | No Update | No Update | Saturn (Larry) to provide outstanding Reports. | Saturn (Larry) to provide outstanding Reports. | Saturn (Larry) to provide on 05/11 | Saturn (Larry) to provide on 15/11 | Saturn (Larry) to provide on 19/11 | Saturn (Steve) to followup with Larry on 29/11 | Saturn (Larry) - sent Report to end of Oct. 2021. GoB (Aran) acknowledged receipt. | Complete
POWER PURCHASE AGREEMENT
| 3 | Execution of Power Purchase Agreement | Saturn | Key Milestones Date | N/A | We note that the amendment agreement extends the dates for achieving the Key Milestones set out in Schedule 1 of the PPA. In particular, we note that the Scheduled COD is now 18 January 2020 and not 18 July 2019. The Agreement for Lease states that the Works Long Stop Date is 18 July 2019. Does Saturn intend to apply to Government to amend the Works Long Stop Date in the Agreement for Lease? | We are working towards the July 18th, 2019 date, however the intention is to align the date with the PPA. Our external real estate counsel will reach out to Simon Benedek to align dates for the PPA Amendment. | Government understands that, in the letter sent by Saturn 19 February 2019, Saturn has requested Government to amend the Works Long Stop Date in the Agreement for Lease to January 18th 2020. Government is awaiting the communication from Saturn's local real estate counsel to proceed with the amendment process. Please note that, as stated in note above, Government will require an explanation of the change in date to begin the process. | We are working with Local real estate counsel to align the dates in the Amendment to the PPA and the Agreement for Lease. Sent letter requesting change. Explanation: Explanation: • We are working aggressively towards the July 18th, 2019 Works Long Stop Date in the Agreement for Lease, however, would like the date to align with the First Amendment to PPA to avoid damages. | Government received email with formal request to amend the agreement for lease. In principle Government agrees with changing the date in the agreement for lease. However, Government will seek for all changes required for the Agreement for Lease to be agreed before it formally approves a change in the date. | Noted | Government have no objection but propose to make all changes to the Agreement for Lease at the same time. | Government have no objection but propose to make all changes to the Agreement for Lease at the same time. | Noted | Saturn awaits response from Government discussion they had with Estates and what requirements will be needed to settle the land lease plan and easement area, etc. Please provide any updates. | GoB. to send draft Agreement | GoB. sent draft revised Agreement for Lease on 18/04/19 asked Saturn for comments. | GoB. sent draft revised Agreement for Lease on 18/04/19. Waiting for Saturn's comments. | Saturn is reviewing and will provide mark-up version shortly. | Saturn is reviewing and response will be forthcoming very shortly. | PPA amendment is currently with BELCO's lawyers who are reviewing the amendment with BELCO. A response is expected shortly. | Noted | 2nd amendment pushing out Target Effective Date to 31 May 2019, and Long Stop Target Effective Date to 31 Aug 2019. Dates on Agreement For Lease need to be revised to match these dates. | No Update | No Update | No Update | Neel has been chasing BELCO. Neel to forward emails to Aran so that he can follow up as well. | Noted | Second PPA Amendment has been signed. | Amendment has been uploaded into data room. GoB to acknowledge receipt. | GoB ackowledge receipt of the Second PPA Amendment in the Data Room | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | Saturn/BELCo amended PPA date to 17/11/21. Saturn to send amended document to GOB. | Saturn/BELCo amended PPA date to 17/11/21. Saturn to send amended document to GOB and upload to the Data Room. | Saturn (Shanna) sent amended PPA to GOB and will upload to Data Room. | Saturn (Shanna) uploaded PPA to Data Room. | No Update | No Update | No Update | No Update | Confirmation required by Government that the final PPA agreement to be uploaded to data room. Simon B sees 7th amendment in the Data Room. Shanna to confirm if it is the latest version. | Shanna confirmed that the latest is the 8th version of the PPA and is in the data room. | No Update | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete
4 | 4 | Confirmation of whether Financial Close has occurred | Saturn | Saturn to advise | In progress | Noted | In progress | Noted | We are close to financial close and will update the Government when it has occurred. | Noted. Please let Government know when financial close is reached. Also, please update Government on the status of including local investment as part of the financing of the project. | Saturn is actively purusing financing options. | Noted | Noted | Saturn is actively purusing financing options. | No update from last week. | Noted | Noted | Any update Saturn? | As Government is aware, Saturn is working with Tortoise. We are currently working together to finalize the security agreements and ancillary documentation. | As Government is aware, Saturn is working with Tortoise. We are currently working together to finalize the security agreements and ancillary documentation. | As Government is aware, Saturn is working with Tortoise. We are currently working together to finalize the security agreements and ancillary documentation. | Noted | Saturn requested Consent to Charge the Benefit of the Agreement for Lease. First draw down is anticipated by Wednesday May 8th. Shanna to follow up. | Saturn and GOB conference call on 08/05/19 to go through revised Financing arrangement. GOB to review information sent by Neel and respond to request to approve the draft fixed and floating charge as changes required to Agreement for Lease. GoB Project Manager sent Ministry of FInance Team all relevant docuements and asked them to review. | Aran sent Ministry of FInance Team all relevant docuements and asked them to review. GoB Project Manager to expedite process and will provide a response by 13/05/19. | GoB Project Manager reponded to Sturn on 13/05/19 - No update. GoB Project Manager will follow up with Ministry of Finance. | Was response provided? | Consent to Charge the Benefit of the Agreement for Lease was sent to Saturn on 20/05/19. GoB requested Saturn provide original signed copy of the original request of 06/05/19. | Consent was provided and the security agreements were executed last week and the first draw down under the note agreement took place on 5/24. | Saturn to provide a press release to GoB so that they can anticipate what questions may be asked by the public. This is currently with Tortoise. | Noted | Saturn awaiting response from BELCO | Gob has provided edits to press release. Saturn is reviewing. | Won't occur until licences are issued | Any Update? | Awaiting for Officer's certificate to be issued. | Noted | Once press release is completed it will be sent to the GoB. | Noted | Officer's certificate has been sent to BELCO for review | Any Update? | BELCO shareholder meeting on Friday August 9th would have been a prioity. Anticipate feedback on this from BELCO soon. | Officer's Certificate to be issued when Bulk Generation Licence is received. | Noted | No Update | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage - Saturn believes Effective Date has been reached? | Officer's Certificate provided BELCO agreed to it. Waiting for BELCo to additional provide information. | No update | No update | No update | No update | No update | No update | No update | No update | No update | Financial Close has not occurred. The Long Stop Effective Date under the PPA arose on 31 December 2019. Saturn is negotiating an extension to this deadline, and other deadlines in the PPA (including to the Scheduled COD - which should remove any threat of liquidated damages). Saturn will provide a copy of the executed amendment agreement in due course. | No Update | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
5 | 5 | Confirmation of whether Performance Bond has been issued | Saturn | Saturn to advise | Performance Bond to be provided on the Effective date under the PPA. | Noted | Performance Bond to be provided on the Effective date under the PPA. | Government understands that Saturn is working towards meeting all the conditions it must satisfy for the Effective Date to arise. In the interest of moving the project forward in a timely manner, and for the Government to be informed of the process, please let Government know as soon as each condition is met. Please bear in mind that according to the PPA, Saturn is required to use all reasonable endeavors to satisfy the Seller Conditions prior to the Target Effective Date. | The Performance Bond is ready. Once the effective date occurs, we will provide. We await Government feedback on when they expect this. | Government looks forward to Saturn informing it when the PB has been posted, and reminds Saturn that Saturn is required to use all reasonable endeavors to satisfy the Seller Conditions prior to the Target Effective Date. While Government has no role in Saturn reaching the effective date under the PPA, Government does need an update on the status of each condition of the PPA. One of the conditions is the Performance Bond. Please update Government when the Performance Bond has been posted. | No further updates from last week. | Noted | Noted | No further updates from last week. | No update from last week. | Noted | Noted | Any update Saturn? | Saturn is working with Belco to finalize language on Performance Bond. | There are 1 or 2 minor tweaks. Should be completed early next week. | There are 1 or 2 minor tweaks. Should be completed early next week. | Noted | John replied back on Friday with a list of questions. Saturn is currently reviewing. | No Update | No Update | Any Update? | Neel spoke with Dennis. Dennis will look at it himself. Neel hopes to have an answer from them by mid-week. | Noted | Awaiting response from BELCO. | Saturn has scheduled a call with BELCO early next week. | Noted | Close to completion. | Working with BELCO. Anticipate completion within a couple of weeks. | No Update | Any Update? | BELCO has signed off on the format of the performance bond. Saturn will follow up with TD bank. | Noted | Verifying the latest version with BELCO. Saturn is circling back with TD bank. THE RA consent is driving the completion of this. | Noted | Updated LC has been sent back to TD bank for issue | Saturn has delivered the performance bond to BELCO along with drafts of its other deliverables under the PPA. | BELCO has confirmed receipt of LC by courier on 7 Aug 2019. | Officer's Certificate to be issued when Bulk Generation Licence is issued. | Noted | No Update | Saturn Performance Bond has been issued | Saturn to Confirm the copy of Performance Bond has been uploaded into Data Room | Saturn to Confirm the copy of Performance Bond has been uploaded into Data Room | GoB - has performance bond been uploaded to the Data Room?? | GoB - please confirm that confirmation of accepatance of Saturn Performance Bond by Belco has been uploaded to Data Room | Saturn to send GoB confirmation of issuance and receipt of Saturn's Performance Bond by Belco | Saturn sent confirmation emails to GoB. and a copy has been uploaded to the Data Room | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
6 | 6 | Consents of Regulatory Authority for license and PPA pass-through | Saturn | Saturn to provide copy of consents | Waiting on building permit processing before we finalize application to RA. | Noted | Waiting on building permit processing before we finalize application to RA. | Government to respond to Saturn with clarification. | We await a response from the Government. | Please update Government when the RA has provided consent. Government notes that the RA is awaiting Building Permit approval before issuing consents. | No Update | Noted | Noted | No Update | Saturn will submit building permit to RA as soon as it’s received so the Government can finish processing our application. | Noted | Noted | Any update Saturn? | Saturn has submitted Generation Licence application to RA. | Redacted version has been shared with the public. | Redacted version has been shared with the public. | Can Saturn provide antipated timeline for the RA issuing license and PPA pass through? | Mike will chase RA for an estimated timeline. | Noted | RA is in receipt of our request and now have 15 days to respond and to raise any issues to us. | Any Update? | RA came back with amendment change requests. Meeting with RA was set up to go over questions. Neel and Karen are working on this. | Any Update? | Saturn has sent a revised RA application to the RA. It is with them for review. RA has up to 90 days to respond. | A second round of questions were asked by the RA. Saturn trying to meet with RA. Aran to be included in the meeting. This item cannot be delayed much longer. | Noted | Comment set 3# is with RA. Mike met with RA on June 12th. | Confirmation that a proper application has been submitted. RA has up to 90 days to review and respond. | No Update | GoB. sent Saturn's License document redaction request to relevant stakeholders within GoB. to review and respond. Will send to Saturn as soon as recevie response from them. | RA has requested a redacted version. The 90 day clock has been stopped until redacted version has been re-submitted. Re-submission expected to occur early next week. | GoB sent Saturn's License document redaction request to relevant stakeholders within GoB. to review and respond. Will send to Saturn as soon as recevie response from them. | Awaiting redacted version from BELCO. Aran has forwarded to government members, and hopes to have it back by end of day July 12th. | GoB's Myron Simmons to send to Neel. Aran has forwarded Nana's response to Neel on 21/07/19 | Awaiting Myron's sign-off on redactions. Neel to follow up with a phone call on 7/29/19 | Saturn submitted redacted versions of the agreement for lease and lease to the RA week of July 22nd | Redactions have been received. Posted on the RA site. | November 28th timeline for approval | Noted | RA review of license application due back November 28th. As this is past the 90 day window Saturn intends to ask for clarity on this. | No Update | Saturn has been in communincation with RA week of Sept. 9th. RA response still expected by Nov. 28th | Saturn has been in communincation with RA week of Sept. 9th. RA response still expected by Nov. 28th | No Update | No Update expected until deadline of Nov. 25th | No Update expected until deadline of Nov. 25th | Skyport asked GoB for opinion on RA's request for clarification of term of Lease vs. the term of PPA on 23/10/19. GoB responded 24/10/19. | No Update | No update | No update | No update | No update | License Application - RA issued Letter to Saturn asking for additional financial information by 31/12/19. | Saturn met with RA on 11/12/19 to discuss delay in issuance of license. Saturn to respond to foraml written request for additional information. | No update | No update | No update | Saturn has submitted all requested information to the RA and has requested a response from the RA prior to 28 Feb 2020. | No Update | Saturn followed up with RA again on 23/01/20. No response as yet. | Saturn received email response from RA on 29/01/20 stating they were reviewing their application | Saturn (Neel) offered to come to Bermuda to discuss progress of license applications further with all parties. | Saturn provided additional information to support application re. financing agreement with Tortoise. RA acknowledged receipt. Doug Wagner (Saturn CEO) sent message to Minister Roban raising same concern about lack of communication/clarity with the RA. | RA responded 14/02 request for additional information. Saturn will respond by 21/02. | RA requested more information 21/02 Saturn responded by deadline. Awatining issue of license on 28/02/20 | RA did not issue license on 28/02/20 but requested further info. Saturn to supply info. On 06/03/20. President of Saturn to meet with RA Board on 11/03. Concern that ACT does not provide specific deadline for RA to respond during this stage. | President of Saturn met with RA Board on 11/03. Additional information sent to RA on 11/03 with additional to be sent on 16/03. Reply expected on 20/03. | RA meeting was productive. President of Saturn able to provide additional information. To date Saturn has provided all information requested. RA acknowledged that Saturn has external deadlines with lender and BELCo etc. Saturn will follow up with RA Week of 23/03. | RA Board meeting week of March 30 to make a final decision. Saturn to provide Government updates as they receive them. | RA Board schedule to meet again week of April 6th re. Bulk Generation License application. Saturn to provide Government updates as they receive them. | RA preparing final formal response documentation to send to Saturn re. Bulk Generation License application. | License Agreement in the process of being completed by Staurn/RA. Saturn asked RA for clarification of what is required to complete. | RA issued license 30/04/20. BELCO supportive of effective date conditions. Pushed out long stop effective date to 31/07/2020 under PPA. Target COD Date 18/12/20. When make Amendments to the PPA will provide those to Govt. | BELCo has acknowledged RA's granting of Bulk Generation License but has not formally responded to Saturn. | Satrun working with BELCo to help make sure remaining conditions under the PPA can be met including approval from RA that BELCo can recover costs assocaited with PPA. | Saturn received feedback from RA re. confirmation of approval of PPA. Saturn sent to BELCo 21/05/20. Uncertainty about status of Grid Code and how this may affect commissioning of system . GoB to clarify with RA. | Saturn has now received new grid code and will review and comment on. At first glance nothing in code should affect commissioning of Project. | No update | Discussions re. PPA w/ BELCo continue. BELCo requested notification from RA that PPA had been approved. RA sent email but BELCo wanted more formal documentation which the RA has agreed to provide. | Progress being made with BELCo. Waiting on RA to issue formal letter week on 22/06/20. | Saturn/BELCO received PPA Approval Confirmation Letter from RA. Saturn discussing with BELCo how to make other conditions of PPA effective. | In Progress | In Progress | Further discussions between Saturn and BELCo and between BELCo and the RA re. delays in COD and Practical Completion. | Executed an ammendment to PPA changed relevant 'Dates' due to delays related to remediation plan (replacement comms. cable). Saturn to provide updated PPA to GoB. | Amended PPA document has been uploaded to the Data Room. No other updates | BELCo PPA - effective conditions/final form in final phase of discussions | BELCo waiting on RA re.approval of cost allocations. Legal opinions on PPA in agreed form. PPA condtions - can then be checked off and PPA approved. | Saturn received PPA Letter from RA and shared with BELCo. Agreed Form of PPA completed waiting on signatures from relevant parties. | BELCo RA Order PPA had taken place - does not immediate BELCo terms however re. recover of costs by consumers not explicity stated in Order. BELCo considering and taking advice. | BELCO conversations with RA re. PPA cost recovery continue. | There is a provision in PPA for BELCo to recover their costs from retail customers associated with the Project. RA provided an order which approves the PPA but BELCO has asked for this to be stated explicity in writing. RA stated that they need further time to consider BELCo's request. Saturn to sent RA Order to GoB. | RA in process of responding to BELCo's request for explicit statement re. recovery of costs. | No Update. Still waiting on RA to respond to BELCo's request and BELCo to sign off on PPA. | BELCo has received 'cost recovery' order from the RA. PPA Execution copy being prepared by Saturn. | Saturn moving forward with BELCo to have all conditions of the PPA finalised. | Saturn moving forward with discussions with BELCo to have all conditions of the PPA finalised. The Legal Opinion, BELCo's request for Insurance and VETO over O&M contrator are the items outstanding. | Saturn still awaiting on BELCo response re. remaining conditions / possible amendments to PPA (veto over choice of O&M contractor/site insurance) | Saturn still awaiting on BELCo response re. remaining conditions / possible amendments to PPA (veto over choice of O&M contractor/site insurance). PPA conditions/BELCo discussing internally. RAB still to approve O&M contractor. | Saturn to reschedule meetings with BELCo to move PPA discussions forward. | Spoke to BELCo re. switching of O&M contractor. Report major changes required by Saturn from RA. BELCO comfort without changing the PPA? To explore further. | Saturn due to confirm and finalise with BELCo and RA re switching of O&M contractor. Saturn will report week of 7/12/20 | Saturn to reschedule meetings with BELCo to move PPA discussions forward. | No material update - BELCo have agreed to push out the requirements for insurance to the O&M Contractor. RA approval pending. | Latest BELCO PPA amendment to be received week of 18/01/21 | Received BELCO PPA ammendment week of 18/01/21 Saturn have call on 22/01/21 to discuss with BELCo. | PPA mark up received from BELCo didn't meet intention of Saturn's request. Saturn to propose new draft which covers issues separately with changes to dates considered first. | Executed PPA ammendment on 31/01/31 to satisfy BELCo wishes. Agreed to provide RA and GoB copy of ammendment and share BELCo email that has been sent to RA. | BELCo/Saturn external counsel finalising legal opinion. Saturn to send PPA amendment and upload to Data Room. | BELCo/Saturn external counsel finalising legal opinion. Saturn hope to have completed by week of 22/02. GoB received PPA amendment document. | BELCo/Saturn external counsel still finalising legal opinion. BELCo acknowledged Saturn's submissions & stated they will respond week of 01/03/20 | Saturn has legal opinion in final form. Have operator approval from RA. Saturn believe they have satisfied all conditions of PPA. GoB (Simon) are there any BELCo conditions that still need to be satisfied? Saturn waiting to hear BELCo's response to this question. | Saturn still waiting to hear from BELCo re. final approval of PPA. | Saturn to continue to follow up with BELCo re. finalisation of PPA - sent outstanding requirements/documents week of 08/03 and followed up week of 15/03 no response, suggested jumping on call with BELCo to expedite. | Saturn still trying to connect with BELCo's new legal counsel on insurance and legal options to satisfy by April 15. | See note below. | Discussions with BELCo new legal counsel - resolutions/corporate docs. Have been sent to Saturn. Opinion should be satisfied. PPA deadline next Thursday April 15th - Long Stop Effective Date which Saturn is trying to meet. | PPA is In Effect as of 15/04/21 (the deadline) | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
7 | 7 | Obtaining of Required Insurance | Saturn | Saturn to advise and provide broker's certificate | We have provided to Aran. | We also note that Saturn has provided us with a certificate of intent in lieu of an Insurance Certificate. Under the PPA, Saturn must maintain “Required Insurance” as defined on Schedule 1 of the PPA. | We will follow-up with our insurers for the insurance certificate. | Please upload the insurance certificate into the data room | We have requested the insurance certificates. | Government acknowledges receipt of the insurance. Please update Government when Belco has approved the insurance. | We are awaiting feedback from BELCO. | Noted | Noted | No Update | Saturn has provided the certificates and endorsements with BELCO and await feedback. | Noted | Noted | Any update Saturn? | BELCO has not provided Saturn on the updates. | Awaiting BELCO feedback. | Awaiting BELCO feedback. | Noted | Shanna will chase on Monday to get BELCO feedback. Steve to provide proof of third party liability coverage. This is needed for advance work to proceed. | Received proof of third party liability coverage. | GOB needs to see that BELCO has signed off on insurance. Neel to follow up. | Any Update? | Waiting for BELCO. | Any Update? | Waiting for BELCO. | Saturn has scheduled a call with BELCO early next week. | Noted | Call with BELCO on 6/13. | Working with BELCO. Anticipate completion within a couple of weeks. | No Update | Any Update? | Saturn is looking to extend expiry from August 1st to October 31st. | Noted | Saturn to follow up to see if BELCO has approved the extension to October 31st. | Noted | No Change | Any Update? | Saturn has insurance ready to go with carrier. | Officer's Certificate to be issued when Bulk Generation Licence is issued. | Noted | No Update | Saturn - Insurnace is in place awaiting sign off from BELCo | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on all remaining approvals at the same time. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on all remaining approvals at the same time. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on all remaining approvals at the same time. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on all remaining approvals at the same time. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on all remaining approvals at the same time. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on all remaining approvals at the same time. | No Update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Saturn to review what insurance requirement is still outstanding and inform GoB. | No update | Saturn agreed to provide update via email. | Saturn emailed and uploaded the Commercially Operational Insurance certificate into the Data Room 06/02/20 | No Update | No Update | Builders Risk insurance will be extended by local insurer as requested by Saturn | Saturn confirmed that Builders Risk insurance will be extended. Documents will be shared with GoB once they have them. | Saturn confirmed that Builders Risk insurance will be extended. Documents will be shared with GoB once they have them | Saturn uploaded copy of document to data room and sent via email to GoB. | No Update | No Update | No Update | No Update | No Update | No Update until operational date | No Update until operational date confirmed. | No Update until operational date confirmed. | No Update until operational date confirmed. | No update | No Update | Builders Risk insurance will have to be extended to allow for implementation of submarine communications cable remediation plan. | Saturn working with Insurance Provider to implement 'steady state' operational insurance to cover Development. | Saturn have moved Development to 'steady state' operational insurance. | No Update | No Update | No Update | No Update | Insurer to visit week of 17/08/20 BELCo to review the results of this visit | Insurer visited site requested additional clean up of site and further clarification of hurricane plan | Satrun responded to Insurers questions. They are happy with additional site clearing and answers provided. | Still waiting for BELCo to sign off on Insurance as it relates to PPA. PPA requires motor vehicle/health and safety insurance. Satrun to negotiate this be carried by O&M Contractor. | Still waiting for BELCo to sign off on Insurance as it relates to PPA. PPA requires motor vehicle/health and safety insurance. Saturn to negotiate this be carried by O&M Contractor. Discussing with B&FM | Discussing with B&FM - certificate of insurance provided by B&FM. Will share with BELCO to see if satisfied. | Continue to work with BELCo on interim solution. PPA in agreed form this is the final area to be concluded. | Continue to work with BELCo on interim solution. PPA very close to agreed form. | Continue to work with BELCo on interim solution. PPA Execution copy being prepared by Saturn. | Continue to work with BELCo on interim solution/resolution to their request for insurance. | Continue to work with BELCo on interim solution/resolution to their request for insurance. | Continue to work with BELCo on interim solution/resolution to their request for insurance. | No Update | No Update | BELCo reviewing insurance proposed by Saturn. | Saturn to confirm week of 7/12/20 | Saturn to provide BELCo with undertaking/acknowledgment that they can review and approve future O&M contractor selection if they provide waiver of insurance for motor vehicle and employees. Saturn to discuss with BELCo on 11/12/20. | No material update - BELCo have agreed to push out the requirements for insurance to the O&M Contractor. RA approval pending. | Latest BELCO PPA amendment to be received week of 18/01/21 | BELCO requested Saturn have employee/motor vehicle insurance before signing off on PPA. Saturn proposed that the O&M contractor will cover these. | BELCO requested Saturn have employee/motor vehicle insurance in-place before signing off on PPA. Saturn proposed that the O&M contractor will cover these. See Obligation #6 | BELCO requested Saturn have employee/motor vehicle insurance in-place before signing off on PPA. Saturn to hire individual and buy motor vehicle and insurance to satisfy BELCo's requirement for insurance. See Obligation #6 | Saturn entered into contract with local employee and purchased vehicle and relevant insurance to satisfy conditions under the PPA which were being required by BELCo. | Saturn entered into contract with local employee and purchased vehicle and relevant insurance to satisfy conditions under the PPA which were being required by BELCo. | Saturn still waiting on insurance confirmation from vendor. Will send to BELCo week of of 03/03/20 . | Saturn recevied insurance and will send to BELCo on 05/03/21 to review and approve. | Saturn sent insurance to BELCo waiting for comment/ approval. | Saturn sent insurance to BELCo waiting for comment/ approval. | Pending still with BELCo | Saturn confirmed they have met with BELCo's new legal counsel re PPA conditions and he is familiarlsing himself with the Agreement prior to responding to Saturn's quesries. | Saturn still waiting on outstanding Insurance sign-off from BELCo. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
8 | 8 | Completion of Financing Agreements | Saturn | Saturn to confirm | In Progress | Noted | In Progress | Noted. Please notify the Government when completed | We are close to financial close and will update the Government when it has occurred. | Noted. Please let Government know when financial close is reached. Also, please update Government on the status of including local investment as part of the financing of the project. | We have sent Aran an email documenting the status of financial close and our efforts spent to date on getting investors. | We received local investment update email from Neel on 15/03/19 and suggested meeting dates with Ministry of Finance on 26/03/19 . Sent meeting request to MoF waiting a response. | Doug Wagner met with Ministry of Finance officials on 03/04/19 to provide local investment update to Government. | Our CEO and CIO has met with the MoF this week. | No update from last week. | Saturn to meet with Minister of Finance on 17/04/19 to introduce International investor. | Saturn to met with Minister of Finance on 17/04/19 to introduce International investor . | Saturn met with Minister of Finance. RA, PS/Minister/Director on 17/04/19 to introduce International investor . | Saturn is actively working to finalize the security documents and should be achieving financial close shortly. | Close to executing financial documents. | Close to executing financial documents. | Noted | First draw down is anticipated by Wednesday May 8th. Shanna to follow up. | Saturn and GOB conference call on 08/05/19 to go through revised Financing arrangement. GoB. to review information sent by Neel and respond to request to approve the draft fixed and floating charge as changes required to Agreement for Lease. | Aran to provide an update on Monday. | GoB Project Manager provided update to Neel on 13/05/19 and followed up with Minister of Finance on 16/03/19. No further update at this time. | GoB to have an answer by Monday | Consent to Charge the Benefit of the Agreement for Lease was sent to Saturn on 20/05/19. GoB requested Saturn provide original signed copy of the original request of 06/05/19. | Consent was provided and the security agreements were executed last week and the first draw down under the note agreement took place on 5/24. | Documents still required are the Sale & Purchase Agreement, ASA, O&M, Security Documents (Share Charge, Fixed & Floating Charge) | Noted | No change | No change | No Update | Any Update? | Pre-Completion funding is in place. Second stage funding is not in place yet. | Noted | Noted | Noted | No Change | Complete | Complete | Officer's Certificate to be issued when Bulk Generation Licence is issued. | Noted | No Update | Saturn to provide certificate | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Stage 1 - Complete Stage 2 - On Going | Officer's Certificate provided BELCO agreed to it. Waiting for BELCo to additional provide information. | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
9 | 9 | Confirmation that Effective Date has occurred | Saturn | Saturn to advise and provide copy of Effective Date Notice | Waiting for generation license and other conditions precedents outlined in the PPA in sections 2.5; 2.10; | Noted | This is the main item we are waiting for (Generation license). The Condition Precedents in the PPA should be satisfied. | Government understands that Saturn is working towards meeting all the conditions it must satisfy for the Effective Date to arise. In the interest of moving the project forward in a timely manner, and for the Government to be informed of the process, please let Government know as soon as each condition is met. Please bear in mind that according to the PPA, Saturn is required to use all reasonable endeavors to satisfy the Seller Conditions prior to the Target Effective Date. | We are using reasonable endeavors to meet the Seller Conditions and will notify + update Government when we satisfy each Condition. | Noted. Please send Government confirmation once each condition has been met. As stated above, Government reminds Saturn that Saturn is required to use all reasonable endeavors to satisfy the Seller Conditions prior to the Target Effective Date. | We have been in contract with Belco's external counsel to close out conditions as applicable. | Noted | Noted | Saturn is working towards closing out all the required conditions. | Saturn awaits update from Government. | Noted | Noted | Any update Saturn? | Saturn awaits BELCO's response. They will have internal meeting early next week. | Saturn awaits BELCO's response. | Saturn awaits BELCO's response from their internal meeting earlier this week. | Noted | Noted | Any update? | Noted | Any Update? | Waiting for BELCO. | Any Update? | Second amendment to the PPA was signed this week. This pushes out the long stop effective date to 31 August 2019. | Amendment has been uploaded into data room. GoB to acknowledge receipt. | GoB ackowledge receipt of the Second PPA Amendment in the Data Room | No change | No change | No Update | No update | No update | Any Update? | No update | Noted | Awaiting RA's approval for Bulk Generation Licence | Saturn is discussing entering into a further PPA amendment agreement with BELCO to push back the Long Stop Effective Date to 31 December 2019 and is also discussing extending the commercial operation dates with BELCO. | Saturn submitted Performance bond and couriered to Belco along with an officer's certificate relating to financial close and authorisations except for generation licence. General feedback: they do not anticipate problems or major hurdles in signing off on those items. Saturn is proposing to push up COD longstop date to end of year and making a 3rd amendment, decision agreed to between Belco's counsel and Saturn; they are reviewing the date internally. Discussed pushing out COD dates and taking back to BELCo. Saturn's perspective, we have to be cautious, because it is possible that BELCO may say that they do not want to push out the dates. | Officer's Certificate to be issued when Bulk Generation Licence is issued. | Noted | BELCo agreed to change the Effective Date of PPA from Dec. 31st 2019 from Aug. 31st. | Saturn to provide confirmation of BELCo agreement to GoB | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on remaining approvals. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on remaining approvals. | BELCo waiting for issuance of Saturn Generaiton Licence before signing off on remaining approvals. | BELCo waiting for issuance of Saturn Generation Licence before signing off on remaining approvals. | BELCo waiting for issuance of Saturn Generation Licence before signing off on remaining approvals. | Stage 1 - Complete Stage - Saturn believes Effective Date has been reached? | Officer's Certificate provided BELCO agreed to it. Waiting for BELCo to additional provide information. | No update | No update | No update | No update | No update | No update | No update | No update | No update | The Effective Date has not occurred | No update | Saturn has received verbal agreement from BELCo to extend Long Stop Date to 31/04/2020 and COD to 18/09/2020. | Saturn will provide GoB with confirmation once BELCo has approved. | Meeting with BELCo week of 10th Feb. to discuss | Met with BELCo. Agree to wait until the issuing of Bulk Generation License to move forward with finalisation of PPA. 4th Amendment drafted. Saturn to send to GoB. | Saturn sent latest PPA Draft and uploaded to Data Room. | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred. Continue to discuss weekly with BELCO to meet any conditions they may have with setting Effective Date under the PPA. | Effective Date has not occurred. Continue to discuss weekly with BELCO to meet any conditions they may have with setting Effective Date under the PPA. | Effective Date has not occurred | Effective Date has not occurred | Saturn - Effective Date will not be affected by completion of submarine communications line remediation work. | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 7 delays re. PPA. | Effective Date has not occurred due to Obligation 6 & 7 delays re. PPA. | Effective Date has not occurred due to Obligation 6 & 7 delays re. PPA. | Effective Date has not occurred due to Obligation 6 & 7 delays re. PPA. | No Update | Effective Date has not occurred due to Obligation 6 & 7 delays re. PPA. | Effective Date has not occurred due to Obligation 6 & 7 delays re. PPA. | Latest BELCO PPA amendment to be received week of 18/01/21 | Received BELCO PPA ammendment week of 18/01/21 Saturn have call on 22/01/21 to discuss with BELCo. | See Obligation #6 | See Obligation #6 | See Obligation #6 | See Obligation #6 | See Obligation #6 | See Obligation #6 | See Obligation #6 | See Obligation #6 | Pending | Pending | See Obligation #6 | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above | Complete - See Obligation #6 Above
CONNECTION AGREEMENT
10 | 10 | Execution of Connection Agreement | Saturn | Saturn to provide copy to Government | We have provided to Aran. | We do not appear to have received a copy of the Connection Agreement dated 20 March 2018 from Saturn. Please send a copy to us. | We will provide. | We received the copy of the Connection Agreement in the Data Room on 25/02/19. Government to review and respond. | Awaiting Government Response | Government acknowledges receipt of document. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
AGREEMENT FOR LEASE
11 | 11 | Provision of Bond | Saturn | Saturn to advise when Bond will be issued | We have provided to Aran. Awaiting Government Response to form of Performance Bond. | Thank you for providing us with an updated draft of the Bond. We originally responded to your request for comment on the Site Bond on January 8th 2018 but appreciate the opportunity to review it once again. We have no legal objections to the Bond document as presented. We will respond with suggestions as to the Date of Issue and Expiry Date as soon as we can. | Thank You, we await Government response re: Date of Issue and Expiry Date | Government is reviewing the bond and will provide Saturn with the Date of Issue and the Expiry Date as well as any comments that may arise from a second revision. | Saturn is expecting dates this week. In the meantime, we have received comments from the Government and are in the process of reviewing. | Government received revised draft of Site Bond and is reviewing. | Saturn to forward on TD's comments to the Government. | Government received latest TD comments on and responded on 27/03/19 to Saturn. Government awaiting for final draft of Bond from Saturn. | Government approved final draft of the Site Bond 01/04/19. Waiting Saturn to issue the Bond. | The Site Bond is finalized. Saturn awaits Government's counsel review. | Saturn has received Government's External Counsel's response and will courier the original L/C, the amendment with the correct address will follow. | Saturn provided copy of Bond 04/04/19. Government requested edits to the address on the Bond 04/04/19. Government confirmed what those changes needed to be 11/04/19. Saturn to courier original bond and amendement to Aran. | GoB. received Site Bond on 17/04/19 - Thank You. Saturn to send Beneficiary address ammendment letter from TD to GoB. | GoB. received Site Bond on 17/04/19 and address amendment letter on 18/04/19. Sent TD signed confirmation letter on 22/04/19. | Saturn notes the Government has signed the Amendmet Letter for TD Letter of Credit Guarantee No. G100185. | GOB received lamendment on Apr 22nd, signed and returned letter to TD on 22nd and received confirmation of receipt by TD. | GOB received amendment on Apr 22nd, signed and returned letter to TD on 22nd and received confirmation of receipt by TD. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
12 | 12 | Appointment of EPC Contractor | Saturn | Draft EPC contract submitted to Government for approval 23/01/19 | With our Board for Final signoff. | The Agreement for Lease requires Saturn Solar Bermuda 1 Limited to obtain Government’s consent before appointing the EPC Contractor and before entering into the EPC Contract. | Saturn has already previously sent the Government the form of the EPC and O&M contracts at the time the Agreement for Lease was executed.. There has been some minor commercial changes, nothing material. Let us know if you want us to send the most current draft. | Government has received a copy of a subcontractor agreement between SSDL and Noesis, but has not received a copy of the general contractor appointment agreement between SSB1 and SSDL. Please provide Government with the most recent draft of the EPC contract. Please also provide a description of the responsibilities of each entity involved in the EPC from the developer to the entity responsible for carrying out the work. Government needs to understand the flow of responsibilities, including the responsibilities between the developer, SSDL, and Neosis. | We have uploaded a word document illustrating the flow of responsibilities into the Data Room. We have also uploaded the EPC and O&M Contract. We await the Government's review and feedback. | Government received the flowchart explaining how the contractual arrangements works, and draft of the subcontracts to Noesis. However, Government has not received the main EPC contract by which Saturn Solar Developments Ltd is appointed as the EPC contractor. Please send Government the copy of this main EPC contract so that Government can review and approve the EPC contractor. | Saturn has uploaded a document that describes the scopes for the EPC (Saturn) and the subcontractor. | The Project Team have no objection to EPC contractor. Have sent a letter of consent to the Minister of Public Works to review and approve. | Letter of consent resubmitted to the Minister of Public Works to review and approve. 29/03/19 | Saturn awaits update from Government. | Saturn awaits formal letter from Minister re: consents | Letter of consent resubmitted to the Minister of Public Works to review and approve. 29/03/19 | Letter of Consent issued to Saturn on 16/04/19 | Letter of Consent issued to Saturn on 16/04/19 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
13 | 13 | Appointment of O&M Contractor | Saturn | Consent application to be submitted to Government in due course | We will select O&M contractor at the mid-point of construction. | Noted | We will select O&M contractor at the mid-point of construction. | Noted | We will select O&M contractor at the mid-point of construction. | Noted | We will select O&M contractor at the mid-point of construction. | Noted | Noted | We will select O&M contractor at the mid-point of construction. | We will select O&M contractor at the mid-point of construction. | Noted | Noted | Noted | We will select O&M contractor at the mid-point of construction. | We will select O&M contractor at the mid-point of construction. | We will select O&M contractor at the mid-point of construction. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | No Update | No update | No change | No Update | GoB. need notification and need to review proposed contract before signing. | Appointment will be made a month or 2 before the project goes operational, most likely in August or September. | Noted | Will be made in August or September. | Noted | Will be made in August or September. | Noted | GoB has requested the right to approve the O&M Contractor prior to appointing them. Saturn is to provide Nana with a letter addressed to the Minister of Public Works indicating Saturn's selection of the O&M contractor. Saturn to upload a copy of this letter to the data room. | Saturn is working on finalizing the O&M contract. Will share with GoB when it is in final form. | Noted | Mid Sept. expectation will send to GoB. | No update | Saturn to provide draft O&M contract/maintainenance schedule by 16/09/19 | Saturn to upload relevant documents to Data Room on 27/09/19 | Saturn uploaded draft O&M document to Data Room. GoB to review and respond. | GoB to review and respond. | GoB to review and respond. AM to follow up with GoB Team | Aran to Speak with Steve Conway | GoB to provide comment by Wed Nov. 6th | GoB to provide comment week of Nov. 11th | GoB to provide comment week of Nov. 11th | GoB. provided comments on 15/11/19. Saturn Responded on 15/12/19. Saturn to provide further details on how the O&M arrangements and how O and M would be allocated between Saturn and Noesis. | Saturn to redraft O&M contract and send a copy to GoB by 06/12/19. | Saturn to redraft O&M contract and send a copy to GoB by 06/12/19. | Saturn to redraft O&M contract and send a copy to GoB by 06/12/19. | No update | No update | No update | Outstanding obligation | Saturn's Investors providing further comment. Saturn to share with GoB once they have received these comments. | Saturn to supply draft version week of 27/01/20 | Saturn Investors still reviewing draft O&M contract | Saturn sent draft O&M contract 07/02/20. GoB to review and respond. | GoB to review and respond by 14/02/20 | GoB to review and respond by 21/02/20 | GoB respond 28/02/20 requesting additional information | Saturn to respond week of 09/03/20 | O&M contract still be worked on, consulting with Lenders and Contractor. Agreed to consider Govt. suggestions in latest draft. | No Update. Govt. awaiting response. | Negotiating with lenders to confirm final versionof document. Early April | Saturn hope to be able provide latest draft 1st week of April | Saturn would like to discuss latest GoB response. Asked for GoB availability for a call week of 20/04/20. | Govt. responded with discussion points document and suggested meeting week of 27/04/20 | Govt./Saturn met to discuss Govt. comments 01/05/20 | Saturn sent latest response to O&M Contract discussions to Govt. 08/05/20. GoB to respond. | GoB - reviewed revised draft. Will provide update week of 25/05/20. Saturn seeking comment from contractors. RA will need to be notified of O&M Contract. | Govt. confirmed had no additional comment at this time. Will wait to receive confirmation of how Saturn decides to proceed with tendering of contract. RA will need to be notified. | Saturn has procured and received additional bids from other contractors. Arranging site visits and will update GoB week of 01/06/20. | Saturn has procured and received additional bids from other contractors. Awaiting comments from vendors/ site visit planned week of 08/06/20. | Procurement Proponent site visits planned week of 15/06/20. | Procurement Proponent site visits planned week of 22/06/20. | Potential O&M contractors site visits completed week of 22/06/20. Saturn awaiting comments from Proponents on Draft Contract by July 3rd. | Saturn awaiting comments from Proponents on Draft Contract by July 3rd. | Two companies being considered for Contract. Comments and pricing to be submitted to saturn by 10/07/20. Company once selected to comment on draft GoB Maintenance Schedule. | Saturn still awaiting further comments and pricing from prefered O&M Contractor. | Saturn recevied comments and pricing from prefered O&M Contractor. Saturn Team to review. | Saturn recevied comments and pricing from prefered O&M Contractor. Saturn Team to review week of 10/08/20. | Selected O&M contractor, Saturn to do final review of contract to send to the GOB and RA to approve. | Selected O&M contractor, Saturn to do final review of contract to send to the GoB and RA to approve week of 31/08/20 before signing. | Selected O&M contractor, Saturn to do final review of contract to send to the GoB and RA to approve week of 07/09/20 before signing. | Terms and Conditions being finalised. Final draft expected soon . | Terms and Conditions being finalised. Final draft expected week of Sept. 21st. | O&M contract going through final legal review by preferred contractor. Govt will need time to consider O&M contract before practical completion date occurs. | Saturn to send GoB final draft version of O&M contract week of 05/10/20. Govt will need time to consider O&M contract before practical completion date occurs. | Reached out to RAB to start review process with them. Govt will need time to consider O&M contract before practical completion/finalisation of leas complete date occurs. | Govt will need time to consider O&M contract before practical completion/finalisation of lease can occur. Long Stop Date- Nov. 30th. | Saturn sent Govt current draft version of O&M contract 19/10. Govt. to review and respond with comments. Saturn submitted request to RA to sign off on O&M contract. BELCO requested that they be given right through the PPA to also approve the O&M operator. Saturn considering BELCo request. | Saturn sent Letter of Comfort to BELCO to address concerns about selection for O&M Contractor. Waiting to hear back from them. | Saturn waiting to hear back from BELCO/RAB re. Saturn's selection process/choice of O&M Contractor. GoB - reviewed Draft O&M contract and has no further comments but will respond formally once it receives the Final Fom of the document from Saturn. | Saturn waiting to hear back from BELCO/RAB re. Saturn's selection process/choice of O&M Contractor. GoB - reviewed Draft O&M contract and has no further comments but will respond formally once it receives the Final Fom of the document from Saturn. | Saturn had response from RA re. O&M appointment - they asked for more information, scope of work, experience of Universal. Saturn preparing a response to RA. | Saturn to speak with RA week of Dec. 30th high voltage experience of proposed O&M contractor. they asked for more information, scope of work, experience of Universal. Saturn preparing a response to RA. | Saturn report discussions are taking place a local qualified HV contractor to perform the work. Saturn to confirm response to RA next week. | RA to approve BAC/Universal as O&M Contractor but requested Saturn subcontract 3rd party for High Voltage work. Saturn to meet with BELCo to discuss them being subcontracted to do this work if required. | Belco have agreed to provide HV qualified technicians to work on the connection works to satisfy the RA requirements. | Waiting for RA approval of execution of contract. BELCO to send contract for HV work 15/01/21. | Finalising BELCo HV support contract after which RA has agreed to approve O&M contract. | Waiting on RA response to Saturn's proposed HV BELCo support proposal. | Saturn has entered into an agreement with US company, along with O/M contractor and BELCo for HV support. Letter sent to RA to this effect which has been acknolwedged. Waiting on RA approval of this proposal. | Saturn still waiting to hear from RA re. approval of OM contractor. | Saturn still waiting to hear from RA re. approval of OM contractor. Will follow up week of 22nd Feb. | RA Approved O&M Contract. Saturn to send GOB amended document for review before executing. GoB (Simon) suggested now is the time to start to discuss the Lease Agreement, Saturn agreed. | GoB (Simon) suggested now is the time to start to discuss the Lease Agreement, Saturn agreed. Satrun waiting for final version of the O&M appointment with Schedule before sending to GoB. GoB will start to prepare related documents once they receive the O&M document. | Saturn has asked and GoB has responded providing comment on the final version of the Agreement. | Saturn sent to Universal for final review, waiting for their response before executing . | The Agreement is with BAC to return to Saturn. | Review by BAC complete and contract excecuted - copy to be posted in data room. | Fully excecuted document to be shared with GoB - copy to be posted by Saturn to data room. | GoB to review the BAC/Universal Contract and get back to Saturn with any questions | GoB to review the BAC/Universal Contract and get back to Saturn with any questions | GoB reviewed contract and have no further comments. Working on Final Form of Lease will send draft of Lease once completed. | GoB reviewed contract and have no further comments. Working on Final Form of Lease will send draft of Lease once completed. | GoB reviewed contract and have no further comments. Working on Final Form of Lease will send draft of Lease once completed. | GoB reviewed contract and have no further comments. Working on Final Form of Lease will send draft of Lease once completed. | GoB reviewed contract and have no further comments. Working on Final Form of Lease will send draft of Lease once completed. | GoB reviewed contract and have no further comments. Working on Final Form of Lease will send draft of Lease once completed. | No Update | No Update | No Update | No Update | Saturn Requested Final Form of Lease | Final Form of Lease. What does the GoB need to do to ensure Final Form of Lease can be executed? | Saturn Requested Final Form of Lease. What does the GoB need to do to ensure Final Form of Lease can be executed? GoB (Simon) to respond. | GoB (Simon) prepared Final Form of Lease. Will share with GoB (Steve/Aran) to review before sending to Saturn. Once Practical Completion notice has been given by Saturn GoB has 10 working days to provide final Lease to Saturn. | GoB (Simon) prepared Final Form of Lease (June 2018) and sent to Saturn. Conatins changed Amendment Agreement, insertion of detail maintanence agreement. Site Access Protocol is missing - GOB asked Saturn to lead this conversation with Skyport/BAA/GoB. Saturn to discuss and revert back to GoB. | Lease - Site Access Protocol is missing - Saturn (Larry) contacted stakeholders Skyport/BAA/GoB to request a meeting to finalise. GoB (Simon) spoke to Saturn (Shana) re.transfer of responsibility for Northern Boundary Fence back to GoB once Project complete. Saturn (Neel) to respond within week with any other changes to Lease Agreement. | Lease - Site Access Protocol meeting with Saturn, Skyport, BAA, GoB on 09/09/21. Saturn (Neel) to respond within week with any other changes to Lease Agreement. | Lease - Stakeholder Site Access Protocol Meeting happened on 09/09/21 - discussed & agreed on access protocols waiting for circulation of minutes by BAA (Ari Ming) which can be reviewed and signed off. Saturn (Neel/Shana) to respond with any other proposed changes to Lease Agreement. | Lease - Stakeholder Site Access Protocol Meeting happened on 09/09/21 - discussed & agreed protocols waiting for circulation of minutes by BAA (Ari Ming) which can be reviewed and signed off on. Saturn (Larry) to followup with BAA. GoB(Simon) offered to draft protocol using his notes if no response from BAA. GoB (Simon) asked for confirmation that Saturn satisfied with Lease in its current form. Saturn (Neel/Shana) to respond with comments. GoB (Simon) need as-built drawings in order to create accurate plan for Lease document. | Saturn (Parth) to arrive on Island 24/09/21 will be on-site to support pre-energisation, commissioning testing with BELCo 27-30/09. Saturn to energise system on 04/10. Access Protocol - BAA (Ari Ming) to provide notes from meeting by 27/09. GoB (Simon) asked for confirmation that Saturn satisfied with Lease in its current form. Saturn (Neel/Shana) to respond with comments. GoB (Simon) need as-built drawings in order to create accurate plan for Lease document. (see 26 below) | Larry's Report - Saturn Engineer [Parth] has been on Island and has completed all pre-energization testing and reports given to BELCO for review. Remaining to do is the Transfer Test Trip as the last test prior to energising site. From that point it will be confirmed that BELCO can control site. Test is due to take place today Oct 1. LH expects by Oct 4th or 5th to be energising the site and then to be able to transfer to the the grid. BELCO have issued caution on ability to attend on site due to potential of Hurricane Sam this weekend. BELCO are also experiencing restraints on staff availability due to Covid. The commercial operational date will declared after satisfaction of the PPA energising conditions. Note - Inverter tests are required to be done in dark on Sunday night to avoid live condition in the day. | No Update | No Update | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete
14 | 14 | Planning Permission | Saturn | Notice to be given to Government within 5 days of grant with a copy of the final planning permission | We will provide. | Noted | We will provide. | Noted. Please upload document into the Data Room when granted | We have uploaded into the Data Room. | Government acknowledges receipt of document in the data room | Completed | Noted | Noted |  |  | Noted | Saturn - Please confirm when Planning Revision Application has been submitted. | Saturn - Please confirm when Planning Revision Application has been submitted. | Any updates to be provided? | Drawings are complete. Larry meeting with Christine Rickards today. Should be ready on Monday or Tuesday. Includes fence, easement,, footprint size, and vault information. | Larry sent revised drawings to Aran on 2-May-19. Note that the set has incorporated the changes that Saturn has requested for the site lease foot print, as well as agreed changes to the cable easement location. Also incorporated is the security fence between the Airside at LF Wade and the Finger. Christine will circulate this revised set to Vicki P. for review prior to submitting the official application to Planning. In the interest of making sure all of the Stake holders are signed off Larry will consult Dave Anderson with regard to the changes and make sure that they can answer any stakeholder concerns for Skyport, BAA and BCAA. | Noted - with thanks to Saturn again for agreeing to include the Fence/Gate application as part of its own Planning Application reveision. | Larry to follow up with Jeannie today with some questions. | As the Fence/Gate is being built by the GOB. The GOB. have agreed with Saturn to address the stakeholder questions as they relate specifically to the Fence/Gate. | Larry will take one last look of the drawings (to the submission of the Planning Permission). If the drawings are satisfactory and send them to the Planning Permission. | GoB has sent Skport proposed drawings for Fence/Gate on 16/05/19 waiting to hear back from them. Any further update re. consultation with Estates on revised drawing set? | On 5/22 Aran confirmed with Vicki Pereira that until she has received written proof of consent from all of the stakeholders she will not be in a position to sign off on Saturn’s Revised Planning Application. Aran has followed up with Sean and Nana of Estates and they have agreed to review the drawings on 5/22. Aran also emailed Skyport to ask for an update on their request to their regulator (ASSI) to approve the fence and gate and is awaiting feedback from them. Therefore, printing and submission of revised Planning Application is delayed until such time that we have all the responses from stakeholders in hand. | On 5/23 Skyport requested clarification of information re. fence/gate. GoB Project Manager has made inquiry with Contractor to answer question and will respond as soon as possible to get final sign off. | Larry to re-submit drawings this week. | The planning group has asked for copies of sign-offs from stakeholders. They are ready to approve once they receive their consent. | Any Update? | Amendment submitted on 6/19. | Revised permit application has been approved by both Planning and Building control. | No Update | Saturn to upload Planning Permission revision consent to Data Room. 4 sets of Drawings still to be supplied by Saturn to Government. | Email acceptance of revised permit application to be uploaded into the data room. Public Works indicated that they did not want to build the fence. Saturn to discuss with stakeholders and investors that they are OK with the removal or change in design of the fence from the plans. | Noted | Larry to supply 4 copies of permit drawings to government | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
15 | 15 | Requisite Consents | Saturn | Copies to be provided to Government for confirmation that they are acceptable | Need Clarification. | Saturn has asked for clarification in respect of item 15 on the Bermuda Solar Project Checklist. Saturn’s obligation is a pure production obligation pursuant to which Saturn must provide copies of all project consents to Government as and when each project consent is granted. | We will provide. | Government received requisite Consents in Schedule B of letter 19 February 2019. These documents have been uploaded to the Data Room | We await formal written approval from Government. | Government acknowledges receipt of document in the data room | Completed | Noted | Noted |  |  | Noted | Noted | Noted | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete | Complete
16 | 16 | Site Access Protocol | Saturn | Saturn to advise of status. Draft to be submitted to Government for approval | We have provided in the form of an official letter. | Saturn has noted in response to item 16 on the checklist that "We have already provided" and in response to item 17 of the checklist "This has been submitted via our planning application". As stated in in our conference call with Saturn on 29th January 2019, any changes requests must be formally documented, such as by an amendment to the Agreement for Lease or by a formal letter of consent from Government. The Government requires therefore that a formal application for consent be sent to Aran McKittrick as the Project Manager. These must be in writing and must be accompanied by supporting documentation. Saturn’s application should also include drafts of any relevant documents (such as a draft Site Access Protocol and any site plan). It is not sufficient for Saturn to refer to documents submitted to another Government Department (such as the Department of Planning). | We will provide. | Government received the Site Access Protocol in Schedule C of 19 February 2019 letter. Government will review to make sure it complies with the minimum requisites and get back to Saturn | We await formal written approval from Government. | Government is reviewing the documents internally and will provide a response to Saturn. | We await formal written approval from Government | Government sent response on this issue 20/03/19, inlcuding comments from Airport Stakeholders. We appreciate Saturn's efforts to finalise the Site Access Protocol after consulting with the stakeholders during meetings planned for the week of April 1st. | Saturn final consultation conference call with stakeholders on 01/04/19 to finalise Site Access Protocol. Waiting final responses from stakeholders before submitting to Government Team. | It is Saturn's understanding that BCAA no longer has any questions or concerns with our project and approvals and that no further studies or reports are required. BCAA is drafting an email response to DOE with Saturn CC’d that BCAA is satisfied with all aspects of our projects and approvals. | Please provide any updates. | Saturn consultation conference call with stakeholders on 01/04/19 to finalise Site Access Protocol. Waiting for formal final submission of Site Access Protocol from Saturn. Any update from Saturn re. confirmation of approcval of Site Access Protocol from all relevant stakeholders? | GoB. received formal submission of Site Access Protocol and proposed revisions and approvals from stakholders from Saturn on 18/04/19. GoB. to review and respond. | GoB. received formal submission of Site Access Protocol and proposed revisions and approvals from stakholders from Saturn on 18/04/19. GoB. reviewed and asked Saturn to upload document to Data Room on 24/04/19. Saturn uplodaed on 25/04/19. COMPLETE | Saturn has received sign off on the Site Access Protocal and we have uploaded the document consolidating responses from Skyport, BAA, and BCAA in the data room. | Saturn to upload final copy in data room when received. | Saturn to upload final copy in data room when received. | Please confirm that this document was not already uploaded to the Data Room? | Saturn confirms that final copy was uploaded to the data room. | Noted | No Update | No Update | No Update | No Update | No Update | No Update | Larry/Mike to confirm if planning group has approved signoffs from stakeholders | Larry/Mike to confirm if planning group has approved signoffs from stakeholders | Final plans have been submitted to GoB showing final location of access road. | No Update | Any Update? | GoB will send a revised Lease Plan Drawing from the using GoB template with Saturn's plans. | Simon sent revised Lease Plan drawing on 08/07. | Construction route is not shown on the plan. To discuss on Monday's call. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
17 | 17 | Location of Substation | Saturn | Saturn to request Government approval to change from NAS to Airport Terminal Substation, accompanied d with supporting information | We have provided in the form of an official letter. | We note that the amendment agreement changes the location of the substation to which the solar facility will connect. Government accepts Saturn’s letter of 31 January 2019 as Saturn’s formal application for consent under the Agreement for Lease to change to location of the Substation from St David’s to the Airport Terminal Substation. | Thank You, please provide formal written consent in a letter for our records. The change in location created a shorter route which we entertained as we thought it would create cost savings. Initially budgeted 13800ft of trenching, cabling and backfill at $65/lf ($897k). After heavy discussion with Skyport, Belco and Dept of Energy, we settled on a submarine cable approach to get out of airside operations to save time. We now only have about 2000ft of trenching and cabling ($130k) but added some environmental study cost, a few termination boxes and 6000ft of submarine cable and installation off a barge at $150/lf ($900k). We should have some added time savings but it comes at a cost. | Government received letter requesting consent on the 31 January 2019 letter. Government notes that Saturn has provided some detail of the differences in costs and timing. Government will send written consent and notes that although Government is to approve the change, Government does not have any responsibility on the effect that over costs or time overruns due to the change will have on Saturn. | We await formal written approval from Government. | Government received request for approval and attaches to this checklist consent to Saturn. | Completed | The Project Team have agreed to approve the relocation of the substation and have sent a letter of consent to the Minister of Public Works to sign. | The Project Team have agreed to approve the relocation of the substation and have resubmitted a letter of consent to the Minister of Public Works to sign. | Saturn thanks the Government. | Saturn awaits receipt of letter of consent once it is signed. | The Project Team have agreed to approve the relocation of the substation and have resubmitted a letter of consent to the Minister of Public Works to review and sign. 29/03/19 | Letter of Consent issued to Saturn on 16/04/19 | Letter of Consent issued to Saturn on 16/04/19 | Completed - Letter of consent already issued. |  |  | Letter of Consent issued to Saturn on 16/04/19 | Letter of Consent issued to Saturn on 16/04/19 | Letter of Consent issued to Saturn on 16/04/19 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
18 | 18 | Location of Access Road | Saturn | Saturn to advise of status. Plans to be submitted to Government for approval | We have provided notice in the form of an official letter. | Refer to item 16. | We will provide. | Government received Schedule E on letter dated 19 February. Document will review and will respond to Saturn | We await formal written approval from Government. | Government received revised Lease Plan from Saturn on 12/03 . Lease Plan sent to Estates for review. | We await update from Government. | Government waiting on Estates to finalise approval of Lease Plan. | Government waiting on Estates to finalise approval of Lease Plan. | Saturn awaits update from the Government. | Any updates from meeting with Estates. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Saturn to respond. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Saturn to respond. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Any update from Saturn? | Saturn is currently reviewing and will provide update shortly. | Included in drawings (line 23) are comments about ease of access to gate 105. | Included in drawings (line 23) are comments about ease of access to gate 105. | Noted | Will remove this line when sign off is completed on planning application. | Noted | Noted | Any update? | Noted | See 23 Above - new location of Access Road is tied to new revised planning drawings | Drawings submitted as part of revised PlanningApplication - approved by stakeholders | Drawings submitted as part of revised PlanningApplication - approved by stakeholders | Larry/Mike to confirm if planning group has approved signoffs from stakeholders | Larry/Mike to confirm if planning group has approved signoffs from stakeholders | Final plans have been submitted to Aran showing final location of access road. | No Update | GoB. to provide final Lease Plan drawings as part of Agreement for Lease amendments. | GoB. to provide final Lease Plan drawings as part of Agreement for Lease amendments. | Simon sent latest version of ammendment to Agreement for Lease on 08/07 containing Location of Access Road | Noted | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
19 | 19 | Changes to Agreement for Lease | Saturn | Saturn to notify Government of any changes requested to be made to the Lease as a result of location of Access Road or changes to the Development t Specification | We have provided in the form of an official letter. | Refer to item 16. | We will provide. | Government received Saturn's letter with request for approval on 19 February 2019 letter, including the map of the new Lease Area. Government is reviewing the documents and will respond to Saturn | We await formal written approval from Government. | Government is reviewing the documents internally and will provide a response to Saturn. | Please provide Saturn on any updates. Saturn has uploaded the lease footprint which shows specifically the interconnection cable location for the easement which will attach to the project land lease. | Government waiting on Estates to finalise approval of Lease Plan. | Government waiting on Estates to finalise approval of Lease Plan. | Saturn awaits update from the Government. | Any updates from meeting with Estates. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Saturn to respond. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Saturn to respond. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Any update from Saturn? | Saturn is currently reviewing and will provide update shortly. | Saturn is currently reviewing and will provide update shortly. | Saturn is currently reviewing and will provide update shortly. | Noted | Noted | Noted | Once plans are in agreed form, we can then make the final changes to the lease. It has come to our attention that we may need an extension to the Site Storage Licence. | Any update? Has Saturn heard from Estates re. extension of Site Storage license agreement? | Saturn to provide update | Any Update? | Nana responded on 5/30 that he does not readily see an issue with the renewal of the licence. Recommends extending for 6 months from the current expiry at the end of July. Saturn to advise. | Larry responded to Nana that Saturn is in agreement to 6 month extension. Nana will issue invoice, and once the invoice is paid, the licence will be issued. Invoice received and paid on June 5th. | Noted | Awaiting a fully signed copy of estates. | Saturn received a marked up amendment to lease and is surprised at open-ended changes at Saturn's cost. Aran and Mike to call Nana to discuss concerns after Simon discusses the changes with Nana. | No Update | GoB to send Saturn current version of amendments to Agreement for Lease | GoB will send a revised plan from the government which is on a government template with Saturn's plans. | Simon sent latest version of ammendment to Agreement for Lease on 08/07 . Saturn requested meeting to walk through. | Walk through scheduled for Monday. | GoB/Saturn went through Amendments. Mike to consult with Neel and team again. Lift and Shift provision to be discussed further internally between GoB and Minister of Public Works. | Awaiting notification of Minister's decision including Saturn's offer to take on construction of fence. Saturn to follow up with Myron on 7/29/19. | GoB/Saturn went through Amendments. Mike to consult with Neel and team again. Lift and Shift provision to be discussed further internally between GoB and Minister of Public Works. | Sign off has been received that the GoB is accepting Saturn's suggestion to deal with the Lift & Shift decision down the road and not at this time. Clearing will resume Wednesday August 14. Saturn to provide a marked up agreement and GoB to act upon provisions. | Saturn provided email confirming Senior Crown Council's communication to Saturn indicating that the Minister of PW agreement to lift and shift recommendations. | Changes sent to Myron Simmons by Simon Benedek for review and approval. | Ask Simon re. update | Changes sent to Myron - Simon will follow up with Myron to confirm he has reviewed them | Simon has requested meeting with Myron to confirm he agrees with GoB changes. Tried to meet with him week of 09/09/19. Simon to ask for rescheduled meeting week of 16/09/19 | Simon sent GoB latest comments to Saturn on 26/09. Saturn acknowledged receipt and agreed to review and respond. | GoB received Saturn latest version. GoB to review and respond. Saturn to respond to GoB request re. providing GIS coordinates of every 20ft in As Built Drawings. | GoB request of Saturn to provide GIS coordinates of every 20ft in As Built Drawings. Saturn believes costs associated will be in $15k to $20k to do so. Steve Conway to ask GoB. Surveyor (Sean Pattteson) and Saturn Surveyor (Jeff Roach) to discuss further in order to reach agreement asap. | Saturn - requested that GoB formally akcnolwedge that they agreed and built the Northern Boundary Fence/Gate if it is not going to be acknoweldged in the Agreement for Lease. GoB to provide a response to request. | Mike - easment on the land has been discussed what about the easement in the water (GPS coordinates on barge when laying the cable). Sean/Geoff. | Saturn to respond with prefered wording. | Gvt has received and is considering Saturn's proposed amendments to the as built drawing requirements set out in the draft amendment agreement. | Gvt has accepted Saturn's requested changes to clause 5 of the draft amendment agreement | Gvt sent clean draft of amendment agreement to Saturn on 21/11/19 for approval | Gvt sent clean draft of amendment agreement to Saturn on 21/11/19 for approval | Saturn reviewing with Investor and once this is complete will be ready to sign the document. | Saturn reviewing with Investor and once this is complete will be ready to sign the document. | No update | No update | No update | Minor comments received from Saturn's funders. GoB responded to Saturn on 10 January 2020 and await sign off from Saturn. | GoB would like to see changes finalized and agreed as soon as possible. Saturn agreed to helping do so. | Saturn has agreed with final changes. Simon sent final draft to GoB Senior Counsel for review. | GoB to provide final draft version of agreement once GoB Senior Counsel has reviewed. | GoB to followup with GoB Senior Crown Counsel for confirmation of approval of final draft | GoB Senior Crown Counsel confrmed no objection to final draft. GoB asked for confirmation for additional information from Saturn lenders. GoB to confirm signing requirements of the Mininstry of Public Works. | Saturn to send. Board approval and lending consent documents to GoB. GoB (Steve) to follow up to confirm no special Ministerial requirements for signing. | Govt. requested that Saturn send another copy of Lending Consent document as illegible when printed. Saturn agreed to do so. | GoB requested that 'Counterparts' part of the agreement for lease be sent by Saturn once it is signed. | Saturn sent 'Counterpart'. Agreement for lease shared with Minister Public Works and asked to sign. Govt. to date documents and return copy to Saturn once complete. | Amendment agreemnt complete. Counterpart sent by GoB to - Walkers, Saturn's Bermuda counsel. Simon to email copy of counterpart to Saturn. Obligation will then be Complete. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
20 | 20 | Plans of the Tenant’s Works | Saturn | Four copies to be provided to Government (after Satisfaction Date) | Awaiting Government Response. | No Response | Awaiting Government Response. | Government is reviewing set of plans titled DWG Set Planning R8 which we received via email on 180119 | We await feedback from Government. | Government is reviewing the documents internally and will provide a response to Saturn. | We await update from Government. | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. |  |  | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. |  |  |  | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. | Government received request from Saturn to strat the Tenant's works. Government repplied to Saturn march 20 with the following: The Government has had further discussions with the Department of Estates (Nana and Sean) with regard Saturn’s revised Land Lease Plan. They have agreed in principal to support your revisions but have asked that the transmission line easement location (and that of the Vault) be moved to the northern end of the central/west tarmacked area (see red rectangle showing this change on the revised Plan attached). If you can revise the plan to capture these changes and send it back to me, we will prepare a final Lease Plan to send to the Minister for his approval. The Department of Planning will need to be notified of this change once it has been approved by the Minister. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | Saturn to provide final versionsof plans when they are ready. | Revised permit application has been approved by both Planning and Building control. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
21 | 21 | Notify Landlord and Insurers of intention to carry out Tenant’s Works | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | We are awaiting approval. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn - Mobilization to occur between May 6th and 10th. Pile-driving to begin between May 16th and 18th. GOB still need to receive formal notification of intention to carry out Tenant's works. | Noted | Format and content of formal notification required of Saturn outlined in email of 16/05/19 to Saturn. | Larry notified GoB of intention to carry out Tenant works. Formal notification needs to be placed in Data Room. | Any Update? | Formal Notice for Construction and Mobilization dated 27 May 2019 issued to GoB by Saturn. | GoB confirms receipt and is satisfied. GoB will issue written confirmation. | GoB responded to Saturn in an email of 31/05/19 and requested changes to the wording and advising that this Notification should be submitted after Planning Approval has been granted. | No change | Saturn has provided GoB with letter of intention to carry out Tenant's Works. | No Update | Any Update? | Simon provided edits to letter of intention to carry out Tenant's Works. Edits were incorporated and re-sent to Simon to review. | GoB received Saturn Letter of Intention to carry out Advance Works and Begin Construction on 09/07/19. Saturn to confirm that insurers have been notified? | Neel to send email to Nana, surveyor, Aran & Simon to confirm. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
22 | 22 | Confirmation Professional Team and other involved in Development will comply with Site Access Protocol | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn - Mobilization to occur between May 6th and 10th. Pile-driving to begin between May 16th and 18th. GOB. will need to receive this confirmation (copy of an email to Professional Team) prior to any work commencing. | Noted | Format and content of formal notification required of Saturn outlined in email of 16/05/19 to Saturn. | Noted | Any Update? | Saturn sent a formal letter notifying the GoB that the professional team will comply with site access protocol. | GoB confirms receipt and is satisfied. GoB will issue written confirmation. (Same notice as line 30) | GoB responded to Saturn in an email of 31/05/19 and requested changes to the wording and advising that this Notification should be submitted after Planning Approval has been granted. | No change | Saturn has provided GoB with letter of intention to carry out Tenant's Works. | No Update | GoB to send Saturn changes to Notification to Start Construction Letter | Simon provided edits to letter of intention to carry out Tenant's Works. Edits were incorporated and re-sent to Simon to review. | Saturn to confirm that Professional Team to comply with Site Access Protocol? | Letter of Intention to begin work dated June 25th addressed this. Simon to speak to Aran and respond. Simon to ask Shanna to upload into the data room. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
23 | 23 | Provide Landlord’s Surveyor with information on progress of Tenant’s Works | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn - Mobilization to occur between May 6th and 10th. Pile-driving to begin between May 16th and 18th. GOB Surveyor (Sean Patterson cc' Aran on all correspondence) will need to receive this information as work proceeds. | Noted | GoB Senior Land Surveyor - Sean Patterson (cc' GoB Project Manager on all correspondence) will need to receive this information as work proceeds. | GoB Senior Land Surveyor - Sean Patterson (cc' GoB Project Manager on all correspondence) will need to receive this information as work proceeds. | GoB Senior Land Surveyor - Sean Patterson (cc' GoB Project Manager on all correspondence) will need to receive this information as work proceeds. | Advance Works letter received and formal notice to begin construction/mobilization issued by Saturn to GoB on 5/28 | Same notice as lines 30 & 31. There in a ongoing obligation to keep the surveyor up to date. Chris Bulley would like to see boundaries marked out by Sean. Aran to follow with Sean to see if there is anything that Sean is waiting on to mark off boundaries. | Any Update? | Sean Patterson came to the finger solar site on 6/13/19 to review and approve the corner pin locations set by Jeff Roach of Qship. Jeff reviewed the pin locations and Sean accepted the work. | Chris conducted final set out, received permit revision, proceeding with construction. | No Update | Noted | Any reference to surveys are to be forwardedto Sudell Joseph who is the acting chief surveyor for July and August. | GoB supplied Saturn with current/ updated MPW Team contact information on 05/07/19 | Aran to follow up with Sudell regarding frequency of reporting. Leaning toward monthly, but will confirm. | GoB requested that Saturn provide schedule of 'milestones' for development and btwn parties will come up with schedule of reporting. | Mike to provide schedule on 7/26/19 | GoB requested that Saturn provide schedule of 'milestones' for development and btwn parties will come up with schedule of reporting. | Mike provided an updated schedule on 10 Aug 2019 | Saturn to upload schedule into data room and send a copy to Sudell Joseph | Noted | Saturn suggested monthly reporting. | Saturn - requested that items 23 thru 26 (obligations of reporting) form part of agenda of meeting with Ministry of Public Works they have requested. | Saturn - still waiting for requested meeting with Minister and PS Public Works as asked in email sent by Neel Bungaroo on 27/08/19 Saturn wish to resestablish good relations with the Government in order to ensure the Projects success but continue to be frustrated by the lack of communication from the MPW with regard this meeting request. Steve Conway to consult with PS MPW to ask about status of meeting. | GoB agreed to a meeting on 1st Oct. to discuss concerns raised by Saturn in Indemnity notices dated 14/08 and 20/09. | GoB - all information to be sent to Steve Conway and GoB Team. | GoB - all information to be sent to Steve Conway and GoB Team. | GoB - all information to be sent to Steve Conway and GoB Team. | No update | Saturn resent Work Plan Nov. 1st. | No update | No update | No update | No update | No update | No update | No update | No update | No update | The trenching works are due to be completed week of 20/01/20. The submarine cable is due to be laid between 21 and 23 January 2020. | Trenching works due to be completed week of 20/01/20 (75% complete). The submarine cable is due to be laid week of 20th or 27th of January depending on arrival of required euipment. | Weather delay of terrestrial trenching. Hoping to be complete 29th/31st Jan. Submarine work due to commence week of 10th Feb. | Submarine cable laying work due to commence week of 10th Feb. Conrete incasement of certain sections of terrestrial cable required in areas of access to new Airport Terminal | Submarine cable laying work 13th--16th/17th - 19th Feb.depending on weather. Kindley Field trenching work due to be complete 10/11th Feb. | Submarine cable laying work to commence week of Feb 24th. Feb.depending on weather. Finger trenching/transformer work due to be complete 7-10 days time. Aiming for substantial completion of project March 1st. GoB to clarify what notification needed to satisfy obligation. | Saturn still waiting on installation euipment for marine cable. Hopeful for practical completion by end of March. | Saturn hopeful marine cable installation equipment will arrive week of March 2nd and work can commence soon after. Trenching work to be completed week of March 2nd | Marine cable installation equipment on Island. Waiting for clearance off Hamilton dock/Customs. Hopeful to complete all work week of March 30th. | Low Voltage trenching work expected to be complete wek of 16/03. Marine cable laying to start 20/03 and be completed within week. | Major construction milestones complete. Terrestrial cable all been installed. Transmission/termination vaults all in place. Loading barge for installation on submarine cable. Cable to go into water 23/03. Overseas Technicians will be available via video link to compelte interconnection as needed. BELCO agreed to allow Saturn to move forward with cable terminations. | Submarine on Barge/laying cable today/complete in 3 days/trenching works for direct bury cable complete/splice at vault at Stone Crusher terminations still to be done/BELCo on Finger re. communications cabling/Saturn team to substation next week to complete interconnection. Substantive completion week of April 8th. 5 day notice still required to GoB for practical completion walk through - Saturn. | Skyport to provide EVPs for a week at a time. Transmission line submarine cable has been installed, splices and terminations complete. Testing to be done with BELCo's support. Hoping to have this work complete by end of day 03/04/20. Will shutdown Airport Finger Site for two weeks as of 03/04/20. Estimate two weeks of work total remaining on the Finger. | Terminations in substation complete. Submarine cable cable testing complete - successful. Continuity testing of complete cable not complete due to Island Wide Lock Down. | Saturn planning on energising the system remotely. NOESIS on stand by ready to complete remainder of work (2weeks est.). Canadian consultant was due to commisson protection and control unit but considering how to do this work remotely. Working with BELCo to complete the interconnection work. Final inspection could be done by independent engineers. | Work Plan being developed for starting work again under phased reopening from 02/05/20. Still intend to commission system remotely. Remaining Project container on Hamilton Dock. | Restarted working on-site week of 4/05/20. BELCO going to site week of 11/08/20 to conduct transmission line tests. Saturn to provide completion schedule estimated to be 2-3 weeks in duration. | Remaining work going well. Successfully completed VLF interconnection test of transmission line. Test of fibre communication line still to be done week 18/05/20. Final panels on site being installed and expected to be complete by 16/5/20. | All modules in place. Clean up of site started. Completing last of connections of the transformers and testing of the system. BELCo installing metering equipment. Working on commissioning schedule. Will provide updates 29/05/20 re. Consultants CIMA+ have provided test plans to do commissioning on using local engineers. | Medium voltage terminiations complete. BELCO meter still to be installed. Termination and testing of SKADA (comms) system still to be done. Protection/Metering testing still to be done. Consultants CIMA+ have shipped equipment to be able to perform testing. | Completing termination of cables on tranformer #2. Solar farm itself largely complete, comms line correction and control still being worked on. BELCo to still install monitoring equipment. Lockdown does continure to affect Project due to not being able to have a Saturn representative on Island to manage completion of Project. In discussions with On-Site Engineering to determine if they have specialised skills to complete remaining testing. Looking to complete Project remotely if flights to Island not resumed in time.Some push back from Skyport with issuing of visitor's passes. | Remaining testing of Medium Voltage cable being done 13/06. Final installation of BELCo and SKADA equip. in progress should be finished week of 15/06. Scheduling of site vists for all stakeholders can be begin soon thereafter. | Very close to completion of construction. Protection and Controls systems still being installed. Testing of cables/larger equipment. Discussing timing of giving notice of completion to GoB. Moving forward with remote commissioning schedule - identified local source for commissioning work. BELCo requested installation of telecomms. pole on site - stakeholders being consulted. Saturn to send GoB site plan of pole location once finalised. | In progress - installation of cellular equipment/BELCO meter/Radio euipment. Skyport/BCAA consulted - requested grid coordinates for telecomms pole. Saturn to provide tree clearing and pole location information/map to GoB. Saturn's debt arrangement with Tortoise - working on another date for repayment due to delay in commerical operation. Phase 2 finacining being worked on and will provide GoB update when able. | BELCo Comms/Metering teams working on site. Finalising Cellular equipment contract, direct bury fibre interconnection. Butterfield Excavation being consulted to do additional clearing work. Saturn to provide Plan drawing of additional clearing area to GoB. No additional response from Skyport/BCAA on additional clearing/installation of comms. pole to date - Saturn to follow up with stakeholders. | Final BELCo meter equipment to be installed July 22-24. Saturn cellular modem to be installed. Saturn still planning for remote commissioning. BELCo and local specialists to help. | One or two venodrs to travel with equipment to Island for Sept. commissioning but Saturn still planning on doing remote commissioning. GoB to issue Letter granting rights to use additional land outside of Lease Area if required. GoB to confirm with Saturn what the area is. | Bid and Scope for additional work for site clearing completed. Saturn asked for GoB. to provide formal approval of additional site clearing BELCo installation of metre completed. Cellular equipment still to be completed for SCADA. Sema Plus protection and control equipment specialists to travel to Island 1st week Sept. | BELCO Meter installed, Saturn SCADA equipment, BELCO antenna pole radio equipment still to be installed Additional clearing will take a week to do once contract in place. Works Long Stop Date has passed. Saturn - requested comfort letter from GoB. GoB to draft letter and send to Saturn. | Butterfield to clear additional trees from site week of 17/08. | Butterfield completed additional clearing. Install antenna and radio comms equipment week of Aug. 31st. Estimated COD middle of Oct. Schedule of Sema Plus tech. Skyport has returned to original security protocol. Certificate of Partial completion provided by NOESIS. Saturn to provide and additional local labour update re. Butterfield excavation. Long Stop Date letter signed by Minister GoB to send to Saturn for signing. | Install antenna and radio comms equipment week of Sept. 7th Additional local labour update re. Butterfield excavation recevied and acknoledged by GoB. Saturn to confirm that Long Stop Date letter has been signed by both Saturn Management and Lender and return digital copy to GoB and upload to data room. | Cell modem being installed 11/09. BELCo work likely to be postponed from 14/09 due to hurricane Paulette. | Damage to six sections of west end of northern boundary security fence due to hurrinace Paulette storm surge. A1 Fence assessed and Saturn issued PO to have it repaired. Butterfield to look at site for physical damage - no visible damage, Saturn to share photos with GoB. All other work was suspended due to Hurricane Paulette. | Saturn to request meeting with Skyport/BAA to discuss long term solution for fence. No other major damage to Solar Farm itself. Weapons Pier East side of Finger took damage and scattered debris under the solar panels. Saturn would like to discuss mitigation of this with Govt. Saturn to provide photos of this to GoB. Road to Clear Water Beach still blocked due to hurricanes. Temporary access granted at Gate 102 to mitigate this. | Install of cellular equipment week of 02/10 BELCO equipment 12/13 Oct. Saturn to follow up with Skyport/BAA to discuss long term solution for northern boundary fence and with A1 Fencing re. schedule of work. Saturn to provide additional photos/video of fence damage to GoB. | Completion of all construction on-site scheduled to be completed week of Oct. 12th. Saturn to send GoB updated construction schedule. Saturn to follow up with Skyport/BAA to discuss long term solution for northern boundary fence and with A1 Fencing re. schedule of repair work. | Belco installations complete. All major work on the Finger complete. . Saturn to follow up with Skyport/BAA to discuss long term solution for northern boundary fence and with A1 Fencing re. schedule of repair work. NOESIS inter-connection contract terminated (Mike to confirm with Neel) working on contracting new developer to install submarine cable. | Requwet for aop from RA spike Wed and RA need exvid ofHV certified contrctor..Larry and Mike to check BELCO HV employees next week.Sub marine cable today and window | Saturn to follow up with Skyport/BAA to discuss long term solution for northern boundary fence and with A1 Fencing re. scheduling of repair work. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No update | Pending - see other updates. | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Saturn (Larry) on Island week of July 5th for 3 weeks. Butterfield Construction mobilising for trench work (July 6th - 18th) starting at Cahow Way. Plan to pull cable, test etc. July 18th -25th. Hoping to be in position to start Commissioning last week of July. Discussions with BELCo re. testing, operations etc. continue. Fibre Optic Cable is on Island. Waiting on proposal from Butterfield (vegetation removal) and Universal Electric (punch list) meeting July 2nd 2021. Saturn to followup with Crisson re. as-Built Drawings (raw data). | Saturn (Larry) on Island - started trenching at Cahow Way, will work 7 days a week to complete the installation of the new comms. cable. Two electricians on the Finger replacing modules, turn off inverters, comms dish being replaced. | Trenching work complete at Cahow Way, started at Kindley Field Road and to be complete by July 18th. Fibrenet to test cable before puts into conduit and then after. 1-2 days to install/test cable, will work 7 days a week to complete.Contractors on the Finger replacing modules, comms dish being replaced. Testing inverters, transformers, programming recloser, testing metering and scadda euipment, BELCO to be on-site to witness all. Skyport RAP passes applied for waiting for Universals to be issued. BELCo/Saturn Meetings continued, move to weekly meeting as commissioning starts. BELCo asked for schedule to be able to confirm/commit resources. | FINGER - eletricians/engineers working on front end commissioning works. Anticpate testing to be completed by 28/07/21. TRENCHING - work to be complete by 25/07. Fibreworks to then pull in cable and do testing - will be complete by 28/07/21. Final Building Permit submission to work of Dept. of Planning week of 2/08/21. BELCo to meet with Saturn on-site 23/07/21, BELCo to provide access to substation to terminate fibre cable. Saturn still meeting with BELCo weekly re. commissioning schedule. Skyport RAP passes applied for waiting for Universals' to be issued. BELCo/Saturn Meetings continue, move to weekly meeting as commissioning starts. | Off-site - fibre comms. cable installed and testing with BELCo input to be completed by end of day 06/08/21. VLF test scheduled for 10/11 Aug. BELCo to be present. Final Inspections by Nigel Daily (Universal) Independent Engineer to do inspection week of 09/08. Saturn to submit relevant documents to Dept. of Planning once this is done. GoB - site visit 12/08. Finger - commissioing work on-site protection and control, recloser (remote switch), SCADA complete. Last step will be the commissioning of the fibre cable itself. Larry on Island 09/08 until commissioing complete. | VLF Test went well results and report due 16/08/21. Fibrecomms Cable Test - two strands have DB loss, back on-site 08/13 to redo. Update on fibre test results expected on 17/18 August. On-site Engineering to provide solutions to flooding in middle of Solar array. GoB - need five clear working days notice for Final Inspection Date. | GoB Engineers on-Site re. Weapons Pier repair/Northern Boundary Gate/Fence repairs 20/08. Section of Fibrecomms Cable being redone on Finger 20/08. BELCo on site 20/08 testing system which is to be witnessed by Universal. On-site Engineering to provide solutions to flooding in middle of Solar array. Saturn (Larry) anticipate 3-5 additional days work before independent inspection by Nigel Daly (Saturn Indpedendent Engineer). Larry last full day on Island 20/08 will be back in a week to 10 days time. | 26/08/21 Fibre comms cable work complete. 31/08/21 BELCo meeting to go over test results. Completion of remaining work will trigger issuing of GoB (Planning) Completion Certificate. Saturn will then provide 5 (clear working) days notice to inspect site for substantial completion. BELCO close to completing own grid upgrade work (1 -2 weeks). Saturn (Larry) met GoB Engineers on-Site reviewed Weapons Pier repair/Northern Boundary Gate/Fence repairs 20/08. On-site Engineering to provide solutions to flooding in middle of Solar array. Larry back on Island 01/07/21. | Hurricane preparation on-going, surge barrier in place on Finger. Larry scheduled to arrive on-Island 07/09/21. New Fibre comms cable in place testing passed, waiting Test document from Fibreworks. Final inspection of interconnection will follow, moving forward with commissioing hoping to be completed 6-10 days COD will follow before the end of Sept. Completion of remaining work will trigger issuing of GoB (Planning) Completion Certificate. Saturn will then provide 5 (clear working) days notice to inspect site for substantial completion. | Larry scheduled to arrive on-Island 15/09/21.Saturn (Kyle) - testing equipment sent to Island in order that Saturn engineer (Parth) can test protection and control systems (recloser) with BELCo 16-17th Sept. BELCo asked for additional testing. Once that is complete can interconnect system and energise. Saturn Fibre Optic Test Report sent to BELCo. Waiting on feedback from BELCo on the testing and interconnection plan. | Followup Test on fibre cable as requested by BELCO complete. Larry to provide test results to BELCo. Independent Engineer to submit report to Planning 20-22 Sept. GOB (Simon) asked for Practical Completion statement. Saturn (Larry) agreed to provide as part of package of dcouments which will be sent to GoB week of 20 Sept. Working with BELCo to finalise Interconnection Plan. COD expected end of Sept. Waiting on more testing equipment to arrive on Island. No damage from hurricane Larry. Vegetation removed from around the site by Butterfield. Vegetation under array still needs to be completed. | BELCO signed off on all fibre comms cable testing. Saturn working with BELCo to finalise Interconnection Plan. COD expected end of Sept. Vegetation removed from around the site by Butterfield Construction. Vegetation under array still needs to be removed. No response from Horsefield Landscaping, Saturn in discussions with Butterfield Construction re. longterm vegetation management proposals. Saturn to discuss with O&M contractor as well as introduce GoB (Steve) to landscape contractor once selected. | See update above. | Sturn (Larry) reported he had a good couple of weeks on site and with only few items to complete to energise. All pre-energise testing has been completed and report given to BELCO. Some final minor punch list items to be done to emergise early next week with a final site walk through planned with BELCO. Interconnect cable the points from diver were given to Q ship last week. Qship has been back to site to check as-builts for the cable and for the transition vault. Final plan will be issued next week. Trench to drain underway. Vegetation removal completed. Storm surge done on Saturn side. Has to be moved for munitions pier repair by GoB. A1 fencing has RAP passes needs schedule for fence change at mercy of Site access. | Saturn (Larry) Commissioning - all pre-energisation tests complete results given to BELCo on Oct. 12th. BELCo happy with results, walk thru of site to take place on Oct. 19th. Expect to energise system on Oct. 20. Discussed review and energisation plan with Joint Technical Committee. Final clean up of site, inverter settings to be done 15/16 Oct. GoB (Simon) - will engineer be able to issue Practical Completion Certificate for site at this time? Saturn (Larry) - Yes. Testing results was final information needed to issue Practical Completion. All test results to be given to Nigel Daly (IE). All survey points given to QShip, they're liasing with Sean Patterson of GoB to be able to provide these for the Lease. GoB (Simon) - how soon will Sturn want/need Lease to be signed? Saturn (Larry) - site will be operation will be opeartional week of Oct. 18th, Easmenet and Site Access Protocol needed to complete Lease. GoB (Simon)- circulated Site Access Protocol to Saturn asked for feedback. A1 still to complete northern boundary fence. 8 Skyport RAP passess provided to O&M Contractor (Universal Electric) - AVOP passes being applied for. GoB Weapons Pier work moving forward. Vegetation removed from around site. Bollards being installed around pad mounted equipment. Dialogue continues btwn Universal and Skyport re. RAP passes. | Energising Site - BELCo asked for inspection of site and requested adddtional cleaning of high voltage equipment - Saturn obliged and completed work. Saturn scheduling re-inspection 25th Oct. with energization set for Oct. 26th/27th = pathway to finishing commissioning. 8 Skyport RAP passes for Universal have been issued, BELCo have applied for RAP passes Skyport agreed to issue EVPs whist these are being processsed. Northern Boundary Fence - no update. Trench for standing water complete. GoB (Steve) Weapons Pier work to be tendered, will update as progresses. GoB (Sean Patterson) - went out to site with Qship to verify location of submarine cable. Route can now be mapped for Easment. GoB (Steve) confirm Sean Patterson to provide Map to him by 27/10. Saturn (Larry) to confirm with Independent Engineer (Nigel Daly) that Site complete and operational in order to meet requirements of Final Completion Letter. Bollard Protection equipment installation to be done on 22/23rd Oct. | Energisation Schedule - anticpate being able to export power to the grid 29/10, BELCO/Universal on-site, Saturn Engineering Team supporting virtually from overseas. Starting with 20% energisation Oct. 30-31 ramping up to 60% to 100% week of Nov. 1st. Final Completion Letter (FCL) Saturn (Larry) to confirm with Independent Engineer (Nigel Daly) that Site complete and operational in order to meet requirements of FCL . All remaining results/documents, physical as-built drawings to be given to IE (Nigel Daly) by Saturn (Larry). What is the format of the letter Engineer of Record Statement? Saturn (Larry) to contat (GoB) Simon to confirm. Lease - GoB ( Steve) sent cable easment plan to Saturn. Saturn to review and provide feedback. Bollard Protection equipment installation to be done on Nov. 2nd. Northern Boundary Fence - no update. GoB (Steve) Weapons Pier - contract finalised w/Butterfield work to be done in coming weeks. Security - Universal now have ten RAP passes and BELCo have three. | Energisation Schedule - 5.1-5.2 MW from site was injected into Grid. BELCO transfer trip test needs 6MW however - planning to do this final test asap. Outstanding tasks to be carried out 5-7/11. Easement Document/Lease Document/Lease Plan - GoB (Steve) Interconnection drawing to undergo one final change which was agreed by Saturn. Saturn will share with BELCo once have a copy. GoB (Simon) provided Practical Completion Statement template to Saturn(Larry) which will be shared with Independent Engineer (Nigel Daly). Bollard Protection equipment installation to be done week of 8/11. Saturn (Larry) suggested that GoB Weapons Pier be coordinated with Butterfield being on-site week of 8/11. GoB (Steve) to confirm this is possible. GoB (Steve) to confirm to confirm if boundary clearing work can be done by Dept. of Parks. Northern Boundary Fence Repair - no update. | Practical Completion Letter hand delivered and acknowledged at Attorney General's Chambers 12/11/21. All systems testing completed. All milestones completed execept Execution of Lease (see 31). Butterfield completing bollard installation 12/11. No response from A1 Fencing. GoB (Aran) to reach out to Allan Whitecross. GoB (Aran) to speak to Robert Richardson re. finalistion of Weapons Pier work. Saturn (Larry) agreed to extend Security escort service until 19/11/21 to facilitate completion of Weapons Pier Work. Transition from Regular Security Schedule from Gate 105 to 102 to happen thereafter. GoB (Steve) to confirm boundary clearing work can be done by Dept. of Parks. | Commerical Operation Achieved - Saturn Solar Bermuda 1 selling power back to BELCo as of 17/11. All major works on site are complete - vegetation clearing, drainage, protection bollards etc. Surge protection barriers out of place but can be moved back in place once GoB Weapons Pier work complete. Saturn transitioning to O&M Phase of Project. Security - change of access from Gate 105 to 102, BUE AVOP Trainning in progress. Working with Butterfield (EVP) passes may be needed, Saturn to move to limited schedule week of 22/11, SA constrained by equipment - Saturn/GoB to coordinate access. GoB (AM) to call A1 Fencing to finalise scope of work with Saturn (Larry) 19/11. Regular Vegetation Maintenance - Saturn will have Butterfield do quarterly inspection, GoB (Steve) to contract to do additional regular site clearing work. | GoB (AM) called A1 Fencing - intend to start clearing the vegetation along the Northern Boundary Fence on 30/11 and then make a start on the repair on the Fence at the end of that week. Weapons Pier Work to start 29/11 - Butterfield to organise own Security Escort. Surge protection barriers out of place but can be moved back in place once GoB Weapons Pier work complete. Regular Vegetation Maintenance - Saturn will have Butterfield do quarterly inspection, GoB (Steve) to contract to do additional regular site clearing work. Saturn to confirm that Skyport had been notified of swtich of use of Gate 105 to 102. | GoB (AM) called A1 Fencing - repair work on Northern Boundary Fence not yet started. Weapons Pier Work started 29/11. Surge protection barriers out of place but can be moved back in place once GoB Weapons Pier work complete. Regular Vegetation Maintenance - Saturn will have Butterfield do quarterly inspection, GoB (Steve) to contract to do additional regular site clearing work. Universal AVOP Training on-going once this is complete Saturn (Steve) to contact Skyport to initiate change over of gates. | GoB (Aran) to confirm status of Northern Boundary Fence work. Govt. (Steve) to confirm status of Weapons Pier work. Surge protection barriers out of place but can be moved back in place once GoB Weapons Pier work complete. GoB (Aran) asked if Saturn's contractors going out to site soon and if so if they could accomodate EVP for Govt. Project Manager. Satunr( Kyle) to check and respond. Regular Vegetation Maintenance - GoB (Steve) to contract Butterfield to do additional regular site clearing work along Northern Boundary Fence. Saturn will have Butterfield do quarterly inspection of the rest of the site. Universal AVOP Training on-going once this is complete Saturn (Steve) to contact Skyport to initiate change over of gates.
24 | 24 | Notify Landlord’s Surveyor of material problems or delays under EPC contract | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn - Mobilization to occur between May 6th and 10th. Pile-driving to begin between May 16th and 18th. GOB. Surveyor (Sean Patterson cc' Aran on all correspondence) will need to receive this information as work proceeds.. | Noted | GoB Senior Land Surveyor - Sean Patterson (cc' GoB Project Manager on all correspondence) will need to receive this information as work proceeds. | Noted | Noted | Noted | Noted | No Comment | No change | No change | No Update | Noted | Any reference to surveys are to be forwardedto Sudell Joseph who is the acting chief surveyor for July and August. | GoB will keep Saturn updated as to any future changes to contacts in MPW. | Noted | Noted | No material problems currently, but tracking the potential problem with the government appointed contractor who stopped work on 7/24/19 due to a lack of contract. This may push back the progress of the EPC contractor. | Noted | Clearing to resume Wednesday August 14 | Clearing did not resume. Saturn issued Indemnity Notice on August 14th. | Noted | Noted | Saturn - no material problems to date. Reiterated delays caused by site clearing work not being completed. | Saturn - still waiting for requested meeting with Minister and PS Public Works as asked in email sent by Neel Bungaroo on 27/08/19 Saturn wish to resestablish good relations with the Government in order to ensure the Projects success but continue to be frustrated by the lack of communication from the MPW with regard this meeting request. Steve Conway to consult with PS MPW to ask about status of meeting. | GoB agreed to a meeting on 1st Oct. to discuss concerns raised by Saturn in Indemnity notices dated 14/08 and 20/09. | GoB - all information to be sent to Steve Conway and GoB Team. | GoB - all information to be sent to Steve Conway and GoB Team. | GoB - all information to be sent to Steve Conway and GoB Team. | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Saturn predicting termination of transmission cable at sub-station week of March 2nd | Saturn hopeful to have practical completion by end of March | Delays due to COVID 19 could occur based on travel restrictions of overseas technical consultants needed to oversee the connection of the transmission cable | Monitoring situation re. COVID 19 Delays could occur. | Monitoring situation re. COVID 19 Delays could occur. | Monitoring situation re. COVID 19. GoV. of Bermuda has enacted 'Shelter in Place' order for Island for two weeks starting 04/04/20. GoB Team to continue to provide official Govt. updates. | No Update | Monitoring situation re. COVID 19. GoV. of Bermuda has enacted 'Shelter in Place' order for Island for two weeks starting 02/04/20. GoB Team to continue to provide official Govt. updates. Saturn expecting final container to be delivered to Island would like clarification on process of receiving if changes required due to Lock Down. Larry to email Govt. details of shipment. | No Update | No Update | No Update | No Update | Saturn assessing potential issue with fibre cable - testing does not show full picture, will continue to provide updates as explore further. | Saturn to review and discuss possible problem with fiber communications cable internally week of 080620. This will need to be fixed if there is any problem before achieve Practical Completion of Project. | Remediation plan for fibre telecommunications cable in place. Saturn hired 3rd party to do testing of cables - report will be produced. New replacement cable spec'd and ordered in case it needs to be replaced. Estimated replacement duration 8-10 weeks. | Submarine Cable Report back - fibre is damaged - exact location identified - remediation plan implemented - new fibre cable going to be installed to address. Estimate 8 -10 weeks. | Remediation Plan immplemented - tracking progress. | Remediation Plan implemented - tracking progress. Expecting to receive coms. cable end of August and install first week of Sept. (3 days install time) | Remediation Plan implemented - tracking progress. Expecting to receive comms. cable end of August and install first week of Sept. Expect COD by Sept.15th. Hoping to shorten schedule if possible. | No update. No change to Remediation Plan Schedule | Remediation Plan - On schedule to receive replacement comms. cable last week of Aug. install first week of Sept. 2--3 weeks duration to install/test. | Remediation Plan on-schedule shipping cable 21/08 receive cable 28/08. | Remediation Plan on-schedule shipping cable 21/08 receive cable 28/08. | Delay in supply of fibre cable until Sept. 3rd. Remediation Plan to be adjusted accordingly. | Delay in supply of fibre cable until Sept. 3rd. Remediation Plan to be adjusted accordingly. | Still a delay in supply of fibre cable. In touch with whoelsaler and manufacturer who are claiming lack of workforce/labour to complete fabrication. Estimated shipping Sept. 18th or 28th. | Cable is at the armoring phase of manufacturing. Still in touch with whoelsaler and manufacturer who are claiming lack of workforce/labour to complete fabrication. Estimated shipping Sept. 28th. | Cable in final stage of manufacturing. Still in touch with whoelsaler and manufacturer who are claiming lack of workforce/labour to complete fabrication. Doubtful will meet shipping date Sept. 28th. Next shipping date from NJ | Cable in final stage of manufacturing. Still waiting for confirmation of shipping date from manufacturer. | Submarine Cable shipping from Florida 09/10 and arrive on Island 13/10. 3-5 day installation period. New cable will be laid alongside original cable. | Submarine Cable shipped awating confirmation of arrival in Bermuda 3-5 day installation period. New cable will be laid alongside original cable. | Submarine Comms. Cable arrived on Island 21/10. Test to be carried out on land 27/10, installation proposed 28th-30th Oct. test in water, complete interconnection and end to end test of entire system. Working on commissioing schedule with BELCo, CIMA + technician to come to Island to assist with testing. | Discussions with Crisson Construction to contract them to complete installation of sub. marine communications cable. Testing of Submarine cable expected week of Nov. 2nd. | Saturn to receive replacement comms. cable from NOESIS week of Nov. 9th. Cable will be pretested by Switch Works (1 day) and then laid by Crisson (3-5 days) weather permitting. CIMA+ will be required to be on Island as part of testing process. Old cable will not be removed as forms part of transmission cable. As Saturn unlikely to meet current Practical Completion Date/Long Stop Date they will provide GoB during week of Nov. 11th 2020 with suggestion for new dates and provide formal response re. reasons for delay so GoB can proceed with process to extend Long Stop Date. | Saturn still waiting to receive new submarine cable from NOESIS. Proposed testing and installation Nov 18-20th weather dependent. Agreement in place w/Crisson Construction, Switchworks to do work. Saturn requested extension to Works Long Stop Date to Jan 31st 2021 via via email. GoB to request Minister provide extension accordingly. | Saturn still in neogtiations with NOESIS for hand over of submarine cable. Legal representatives from both parties meeting 20/11/20 to move conversation forward. Switchworks to test cable before purchase completed. Northern Boundary Fence meeting set for week of 25th Nov. 2020 - GoB/Saturn/Skyport/A1 Fencing to attend. | Agreement in place with NOESIS to receive submarine cable. Switchworks to do testing 2/12/20. If satisifed Crisson Construction will schedule install in the days after if presented with weather window. Meeting with Skyport and Saturn re. Northern boundary fence - suggestion to install conrete barriers to protect new fence. Porposal to be drafted by Saturn and sent to Skyport for them to get the relevant approvals BAA/BCAA. | Northern Boundary Fence - Saturn to send plan to Skyport to accept. Skyport to provide wording of Warning Sign. GoB Engineers suggested using ash/concrete blocks made at the Airport dump as a more economical solution and can be trucked around by land. GoB to check details and report back on it. | Submarine Cable has been tested - passed. Crisson arranging pickup of cable and waiting for weather window for installation of cable. Switchworks visited Finger week of 30/11/20 preparations for terminations and testing of cable. Crisson to do additional work at Helipad vault to facilitate installation of new comms. cable. Northern Boundary Fence - ash blocks not suitable as extra protection but GoB willing to provide concrete barriers as an alternative. Saturn to consult further with GOB and A1 Fencing. | Submarine cable was installed by Crisson on 24/012/20. Switchworx terminating cable and testing 8/01/21.Commissioing expected to start on the week of 18/01/21. Commissioning duration 10 to 14 days. Saturn team expecting to travel to Bermuda to attend commissioning and will check latest Bda Covid requirements for travel from US and Canada. Saturn team from Canada intending to come via US East Coast. Northern Boundary Fence - Larry to mark up plan to show how the end will be reinforced at the wateredge for agreement with Skyport. | Termination, testing, OTDR End to End test of submarine cable to completed 18/01/21 . Schedule for commissioing will then be started. Tech. protect and control team from Quebec won't be able to come to Bermuda due to COVID, looking for alternative. Hope to start commissioning last week of January/first week of February. Crisson clearing up surplus equipment for storage. Northern Boundary Security Fence - Saturn to follow up with A1 Fencing with schedule to complete repair work. GoB can provide 3 x 10ft. blocks for fence protection purposes. | Fibre terminated end to end 21/01/21. OTDR test inconclusive will be redone week of 25/01/21. Asked BELCO to redo power component (VLF) test as well. Saturn to have call with BELCo re. commisioning schedule. New Commissioning company's proposal being reviewed by Saturn. No update on Northern Boundary fence Saturn to follow up with GoB and A1 Fencing. BELCO HV support discussion with RA continuing. Switchworx contracted to do other inspection works on site. | Testing week of 21/01/21 postponed due to extreme weather rescheduled for week of Feb. 8th. Saturn notified by BELCo of potential further delays to commissioning of system due to BELCo network systems updgrade. Saturn asked for a call with BELCo and all stakeholders. Will let GoB know once hear back from BELCo re. date/time. No responses from A1 Fencing. Saturn to contact again. | No testing carried out last week. BELCo was not availabile. Waiting on BELCo for access to BAT confirmation week of Feb.9 - 11th. Still waiting on BELCo for request for stakeholder meeting. A1 Fencing Allan/Gerard Whitecross still no response re. schedule for repair of Northern Boundary Fence. Saturn/GoB to try and contact again. | New comms. cable test on 11/02/21 completed but no results as yet from Switch Works. Saturn will confirm result once receive it. Requested new VLF interconnection cable test from BELCO, waiting for agreement from them. BELCo agreed to meeting with Saturn and GoB on 16/02/21 to discuss possible interconnection delay. GOB to confirm reason for delay given by Staurn with internal Govt. stakeholders. Saturn to confirm A1 Fencing Allan/Gerard Whitecross completed repair work on Northern Boundary Fence. | New Comms. Cable - Saturn received testing report 10 of 12 fibre strands passed 2 showed high loss, believe issue is in the vault not in the cable. Only 4 of 12 will be used. Results will be provided to BELCo. BELCo also asked for a OTDR Test on Fibre. New VLF test also to be done in next week or two. Once tests are completed to Saturn/BELCo's satisifaction can move to scheduling/commissioning. No update on A1 Fencing Allan/Gerard Whitecross completed repair work on Northern Boundary Fence. | Switchworks on site 26/02/21 to re-splice comms. cable connections. BELCo has granted access to vault to retest relevant fibres. Discussing test results with BELCo. BELCo accepted VLF Test request hoping to be done week of 01/03 or 08/03. Saturn (Larry) to still to contact A1 Fencing Allan/Gerard Whitecross to confirm completion of repair work on Northern Boundary Fence. Saturn asked GoB (Steve) to provide three concrete road barriers to shore up fence on waterside, as offered. | Saturn continues to discuss testing protocol on cable with BELCo. Engaging third party to validate testing. Power meter testing within acceptable threshold, OTDR test was not. BELCo asked Saturn to retest, from both sides of connection (Finger/Substation). A1 Fencing work delayed due to issuing of security passes. A1 scheduled to do work/repairs including placement of concrete blocks which will be anchored to fence week of 8/03/21 | No consensus between Saturn/BELCo on testing standards (Power Meter and OTDR test ) of new comms. cable. BELCo requesting Saturn's analysis/interpretation of data that has been produced from the tests. Saturn to engage 3rd party to verify data and do this analysis. No update on repair of Northern Boundary Fence - A1 still to get back with repair schedule, Saturn (Larry) to arrange movement of reinforcing barriers to site. | Switchworx on site 17/03/21 - redoing/cleaning up splices/connections in order to re-run tests on comms.cable. Saturn has proposed forming a Technical Committee to move approval process forward. Hoping tohave first meeting week of 22/03/21. A1 Fence no update. | Switchworx have been on site this week testing fibre optic cable. Testing is providing better results against the prescribed thresholds. Saturn is now working with BELCO on a Joint Technical Committee and met on March 25 to agree purpose of the group, set protocols and a test plan. Target date for connection now May 31. | The Joint Technical Committee met this morning for Saturn to coordinate with BELCo on the connection issues. Saturn confirmed further testing by Switchworx this week and next week. Further investigation as needed at the splice at the manhole at the Stone Crusher Corner where a higher loss is experienced. Saturn to report on results. | Delay -due to exposure to Switchworx Team who are now under mandatory quarantine until 18/04/21. Final fibre cable remediation work to be rescheduled as and when they are able to do it. Crisson Construction to help with placement of barriers on Northern Boundary Fence - week of 12/04. Dialogue with Technical Committee discussions progressing meeting every two weeks. | Switchworx Cable Technicians in quarantine until 19/04. Upgrades planned for the splice at the vault at Stone Crusher Corner. Punch List of outstanding tasks being developed btwn Saturn and BAC/Universal. Future Access to Finger being discussed with Skyport. RAP/AVOP Pass will be required to gain access through Gate 103 once Project completed. Skyport to coordinate conversation with all stakeholders re. future access and use of access road.GoB suggest walk-through between GoB/Saturn when closer to commissioning. Dialogue with Saturn/BELCo Technical Committee discussions progressing meeting every two weeks. | Scheduling airport security access for week of April 25th for Upgrades planned for the splice at the vault at Stone Crusher Corner. Testing and Results to come thereafter. Punch List of outstanding tasks being developed with BAC/Universal. Future Access to Finger - Saturn to coordinate conversation with all stakeholders.GoB suggest walk-through between GoB/Saturn when closer to Project Commissioning. GoB request for as much notice as possible re. Final Inspection. | Commissioning planned for first two weeks in June, dependent on BELCo's approval of repair of fibre cable work and their readiness to interconnect. Skyport Security Acces Pass application process streamlined . Saturn to rengage with Skyport re. meeting on long term access to Finger. GoB asked for 'As-Built' drawings for landing of cable onto Finger as per Section 5 of the Implementation Agreement. Testing of comms. cable continues believe that section of cable from Finger to Vault is good. Believe fault is from Stone Crusher corner to Substation. GoB request for as much notice as possible re. Final Inspection. | Switchworks on-site continuing to isolate comms. cable issues. Saturn hired 3rd party consultatnt to interpret fibre comms cable test results, to share with BELCo soon. Saturn to followup with QShip/Crisson for 'As-Built' drawings for landing of cable onto Finger as per Section 5 of the Implementation Agreement. Saturn to re-engage with Skyport re. meeting on long term access to Finger. | More testing on comms. cable done. Additional results to be reviewed by US specialist. Expect response in a week. Acceptable test results on End to End test. Individual segments test show losses which are above threshold in some cases. Saturn has followed up with QShip/Crisson for 'As-Built' drawings for landing of cable onto Finger hope to have update week of May 17th. Saturn to re-engage with Skyport re. meeting long term access to Finger. BELCo/Saturn Technical Committee met 13/05/21 - discussed about operating procedures. T&D upgrades estimated to be complete by BELCo 1st week of June. | Saturn continue to evaluate fibre cable. Saturn bringing on more resources to resolve the issue and for commissioning. Larry to travel to BDA 1st week of June. Saturn to request trenching permit from Works and Engineering/BAA for Kindley Field Road. Universal on-Finger week of 24th May to continue work on 'punch-list'. Will followup with Qship/Crisson re. As-Built Drawings. GoB to reach out to BAA to confirm what role they will play in GoB/Saturn's long term access to the Finger. Saturn to re-engage with Skyport re. timeliness of access and security protocols. | Saturn (Larry) in Bermuda on 6/6/21 for two weeks. Considering replacement of comms. fibre cable from junction at Heli-Pad/Cahow Way to new sub-station. Replacement Cable in US but can be shipped in 2-3 days. Saturn in communication with GoB (W&E) for trenching permit. Will install conduit along Kindley Field Road whilst waiting for cable to arrive. Saturn to followup with Qship/Crisson re. As-Built Drawings. GoB (Steve Conway) to reach out to BAA (Ari Ming) directly to confirm long term security and access protocols. Saturn willing to attend meeting with all stakeholders if organised. | Remediation of Fibre Optic Cable commenced from Heli-Pad vault to Cahow Way to new sub-station. Cable and conduit sourced. D&J/BAC helping with remediation. Saturn in communication with GoB (W&E) for trenching permit. Will install conduit along Kindley Field Road whilst waiting for cable to arrive. Saturn to followup with Qship/Crisson re. as-Built Drawings - scheduled meeting week of June 14th. Meeting with Butterfield Excavation/O&M Contractor re. development of on-site vegetation management. BELCo/Saturn Technical Committee meetings continue. - BELCo projecting to complete network upgrades by end of June. | Fibre Optic Cable has been ordered and shipped. Completed submission of trench permit to GoB (Works and Engineering). BAA has been consulted. Meeting with BELCo 18/06/21 at substation. Met with Butterfield Construction (vegetation removal) and Universal Electric - to develop punch list. GoB (Steve) to confirm to Saturn what can be done re. vegetation abatement. Site visit planned with GoB/Satun in July. Storm surge has pushed debris under solar array. Saturn suggesting to address using concrete barriers. Saturn to followup with Qship/Crisson re. as-Built Drawings - scheduled meeting 18th/19th June. | Saturn (Larry) on Island for last week of July. Fibre Optic Cable has been ordered and to be shipped week of June 28th. Trench permit issued for July 2nd to 12th. Consulting with BAA/Skyport re. traffic management. Met with BELCo 18/06/21 at substation - found 4" BELCo conduit which will use for new fibre from Stone Crusher corner to new substation. Working with Butterfield Construction to do trench work. Waiting on proposal from Butterfield (vegetation removal) and Universal Electric (punch list). GoB (Steve) confirmed to Saturn what can be done re. vegetation abatement (use of Tordon). Saturn to followup with Crisson re. as-Built Drawings (raw data). Larry proposed return to Bermuda July 7/8th for Commissioning. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | EPC Contract - GOB (Simon) asked Saturn (Shanna) to upload copy of fully executed EPC contract to the Data Room. | EPC now in Data Room | No update | No update | No update | No update | No update | Complete | Complete | Complete | Complete | Complete
25 | 25 | Provide Landlord’s Surveyor with 5 working days’ notice of all meeting in connection with the progress of the Tenant’s Works | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | We are reviewing comments for an amendment to our final plans. | Noted | Noted | We are reviewing comments for an amendment to our final plans. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn - Mobilization to occur between May 6th and 10th. Pile-driving to begin between May 16th and 18th. GOB. Surveyor (Sean Patterson cc' Aran on all correspondence) will need to receive this information as work proceeds. | Noted | GoB Senior Land Surveyor - Sean Patterson (cc' GoB Project Manager on all correspondence) will need to receive this information as work proceeds. | Noted | Noted | Noted | Noted | No Comment | No change | No change | No Update | Saturn to notify sudell and nana of these meetings | Any meetings with contractors to be communicated to GoB to allow them to send a representative if they so choose. | Noted | No Update | Noted | No Update | Noted | No Update | No Update | Noted | Noted | Noted | Saturn - still waiting for requested meeting with Minister and PS Public Works as asked in email sent by Neel Bungaroo on 27/08/19 Saturn wish to resestablish good relations with the Government in order to ensure the Projects success but continue to be frustrated by the lack of communication from the MPW with regard this meeting request. Steve Conway to consult with PS MPW to ask about status of meeting. | GoB agreed to a meeting on 1st Oct. to discuss concerns raised by Saturn in Indemnity notices dated 14/08 and 20/09. | GoB - all information to be sent to Steve Conway and GoB Team. | GoB - all information to be sent to Steve Conway and GoB Team. | GoB - all information to be sent to Steve Conway and GoB Team. | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Communication with John Pears of Skyport re. use of barge crane in close proximity to Airport and route of submarine cable. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | No update | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | No Update | No Update | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | Independent Engineer's Inspection completed. Saturn waiting on report. Will send to GoB (Planning). GoB to review Engineer's Report once received and discuss with Saturn. | Independent Engineer's Inspection report received by GoB on 22/09. See obligation 27 below. | LH to update as above. | Waiting on full and final testing. See LH report | No update | No update | No update | No update | Complete | Complete | Complete | Complete | Complete
26 | 26 | Provide Landlord with 5 working days’ notice of Independent Engineer’s intention to inspect the Tenant’s Works with a view to issuing Practical Completion Statement | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we complete work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn to notify GoB Projet Manager via email. | Noted | Noted | Noted | Noted | No Comment | No change | No change | No Update | Who is the independent engineer? Falls under EPC Contract obligations. Mike to let GoB. know. | The independent engineer will likely be the person who signs off the permit and participates in the practical completion meetings. | Noted | No update | GoB asked for independent surveyors credentials (CV) and contact information which will be shared with relevant GoB Team members. | Mike is waiting on a schedule assurance of availability and will provide information to GoB. | Saturn provided Independent Engineers details to GoB on 31/07/19. MPW to confirm that this is sufficient. | Mike provided details of the independent engineer in an email on 31 July 2019. Mike to forward a copy to Sudell Joseph. | Mike to copy Nana when forwarding a copy to Sudell Joseph | Noted | Milestone meetings will happen. Combine with 25 above. | Saturn to follow up with Indepenent Engineer for reports. | Saturn still watinging for independent engineer's reports. Will notify GoB when these have been received. | Saturn - Ed Periera (structural engineer) has been hired along with Kennedy Wainwright (electrical engineer) to provide the independent engineer's reports. Expecitng Reports week of Oct 1st. | Saturn - have electrical engieering report to send waiting on structural report. Will send both at same time. Delay in reporting due to Hurricane Humberto. | GoB received electrical engieering and structural report. Will review and comment accordingly. | GoB to review and respond. AM to follow up with GoB Team | GoB requested that Saturn provide Engineer's stamp/signature on reports provided. | No update | No update | No update | No update | No update | Independent Engineer inspected Site week of Dec. 2nd. Expected to return week of Dec. 9th. Saturn to notify Govt. when they know the date. | Independent Engineer inspected Site week of Dec. 2nd. Expected to return week of Dec. 9th. Saturn to notify Govt. when they know the date. | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Structural Engineer to do site survey week of 16/03. Saturn to supply report once they receive it from engineer. | Structural Engineer survey did happen week of 16/03. When report is complete Saturn will provide GoB Team | Will provide week of March 30th | Saturn has Electrical Inspection Report waiting on Mechanical Inspection Report. Will forward them week of April 6th. | Issuing of Reports delayed due to Lockdown. Saturn will provide them as soon as they receive them from engineers. | Saturn will provide the independent engineer's report as soon as they receive them from engineers. Stuctural Report available to be sent to GoB Team 24/04/20 | Structural Report to be sent 01/05/20. | Structural Report was sent to GoB 01/05/20. Remaining Tasks; terminations complete, modules need to be installed . Testing of the full length oftransmission cable (BELCO), testing fibre optic cable, BELCO won't energise until above is done. 3rd Party protection and control cabinet installed on-site but also needs to be tested. Vendor intended to do commissioning work but plan to possibly subcontract to local engineer's to do the work. Saturn responsible for triggering Practical Completion and Effective Date. Saturn need to satisfy certain conditions to BELCO before doing so. | No Update | No Update | Discussions with BELCo's engineering team moving forward. Saturn hoping to provide BELCO detailed and accurate a completion schedule as possible. Will update GoB update at same time. Estimated Practical Completion mid-June 2020 | No Update | No Update | No Update | Practical completion will occur when remediation work on submariune cable completed. | Practical completion will occur when remediation work on submariune cable completed. | Practical completion will occur when remediation work on submariune cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. Saturn to provide latest remediation schedule to GoB which will indicate when final inspection will take place. Practical Completion will occur on that date. | Practical completion will occur when remediation work on submarine cable completed. Practical | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. Due to Xmas holidays any review of Practical Completion Statement by GoB may be delayed to week of Jan 4th. 2021. | Practical completion will occur when remediation work on submarine cable completed. Due to Xmas holidays any review of Practical Completion Statement by GoB may be delayed to week of Jan 4th. 2021. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | GoB - notice should be provided by Saturn once testing of interconnection cable has been completed. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn scheduling request for final building permit (Dept. of Planning) and independent engineer's final inspection. | Saturn asked for issue of final Certificate of Completion and Occupancy by Dept. of Planning. | Saturn asked for issue of final Certificate of Completion and Occupancy by Dept. of Planning. Planning outlined final procedure to Saturn. Saturn asked for reports from independent engineers to satisy requirement. | No update - waiting for BELCo and Saturn to agree and sign off on comms. cable before requesting Final Certificate of Completion and Occupancy from the Department of Planning. | Saturn is concerned about BELCo's u/g infrastructure upgrades at the East end of the Island further delaying Saturn's connection and request if the Government would be willing to give a word of encouragement to BELCo and emphasise the high priority of the project completion to the Government. LH has been in contact with Crisson about barging over the precast barriers from GoB Quarry to support the shorline ends of Airport boundary fence. Will report next week dependent on weather conditions in Castle Harbour. | SC confirmed the PS for Public Works called a senior contact at BELCo to emphasise the the importance to the Government of the completion of the project. BELCo acknowledged and noted that Saturn still has some final work and testing to close out completion for the connection. On the Airport fence end - LH confirmed he has been in touch with PW Quarry re the reserved precast barriers. The units will come by barge or truck depending.Timing to be confirmed subject to Crisson barge availability in Castle Harbour- or will be by truck with Butterfield Excavation support. | Saturn appreciate Govt. having reached out to BELCo directly to move coversation forward. | No update from Crisson re. Northern Boundary Fence. Saturn to get Update. | A1 Fencing ready to do repair work on Northern Boundary Fence. GOB Barriers ready to be picked up when Crisson Construction ready to deliver. | Saturn to follow up with A1 Fencing re. progress on repair of Northern Boundary Fence as well as status of pickup and placement of GoB concrete barriers by Crisson Construction. | Saturn to follow up with A1 Fencing re. progress on repair of Northern Boundary Fence as well as status of pickup and placement of GoB concrete barriers by Crisson Construction. | Saturn to follow up with A1 Fencing re. progress on repair of Northern Boundary Fence as well as status of pickup and placement of GoB concrete barriers by Crisson Construction. | Saturn to follow up with A1 Fencing re. progress on repair of Northern Boundary Fence as well as status of pickup and placement of GoB concrete barriers by Crisson Construction. | Saturn to follow up with A1 Fencing re. progress on repair of Northern Boundary Fence as well as status of pickup and placement of GoB concrete barriers by Crisson Construction. | GoB (Aran) to follow up with Alan Whitecross (A1 Fencing) re. progress on repair of Northern Boundary Fence. Saturn (Larry) to followup with Crisson re. pickup and placement of GoB concrete barriers. | GoB (Aran) followed up with Alan Whitecross (A1 Fencing) re. progress on repair of Northern Boundary Fence - delays caused by Skyport issuing security passes. Saturn (Larry) to followup with Crisson re. pickup and placement of GoB concrete barriers. | No update | GoB (Aran) followed up with Alan Whitecross (A1 Fencing) re. progress on repair of Northern Boundary Fence - delays caused by Skyport issuing security passes. Saturn (Larry) to followup with Butterfield Construction re. pickup and placement of GoB concrete barriers. | Satrun (Larry) Meetng A1 Fencing on-site on 12/07 re. Northern Boundary Fence and Crisson Construction on 13/07 re. as-Built Drawings (raw data). | Saturn (Larry) to followup A1 Fencing on-site on 19/07 re. Northern Boundary Fence and Crisson Construction on 19/07 re. as-Built Drawings (raw data). | Saturn (Larry) to followup A1 Fencing on-site on 23/07 or 24/07 re. Northern Boundary Fence and Crisson Construction on 23/07 re. as-Built Drawings (raw data). | Saturn (Larry) met with A1 Fencing on-site re. Northern Boundary Fence. To followup with Crisson Construction re. as-Built Drawings (raw data). Saturn requested proposals from local contractors for vegetation management. | A1 Fencing still having issues with security access to repair Northern Boundary Fence. Estimate 3-4 days to complete work. Saturn to followup with Crisson Construction re. as-Built Drawings (raw data) for submarine cable. Saturn requested proposals from local contractors for vegetation management plan. GoB (Steve) requested that GoB come to an agreement with vegetation contractor to do additional work on the Finger if required. | No Update on A1 Fencing still having issues with Skyport security access to repair Northern Boundary Fence. They estimate 3-4 days to complete work. Saturn to followup with Crisson Construction re. as-Built Drawings (raw data) for submarine cable. Saturn asked for proposals from local contractors for vegetation management plan. GoB (Steve) requested that GoB come to an agreement with vegetation contractor to do additional work on the Finger if required. | Qship have terrestrial data for As-Built drawings but still need marine cable location data from Crisson. GoB (Simon) asked for Saturn to provide data once in possession. No Update re. A1 Fencing - still waiting on RAP process. GoB delieverd 6 concrete barriers to Project site. GoB engineers approved Saturn's storm surge design. GoB (Engineers) suggested 90 degree support braces to Northern Boundary Fence as opposed to using concrete barriers. Saturn will give instruction to A1 Fence to do this work. Vegetation proposals still waiting on Horsefield Landscaping. Butterfield will clear access road way. A1 Fencing to clear vegetation along northern boundary fence line. | Saturn (Larry) to follow up with Crisson As-Built drawings. GoB (Simon) asked for Saturn to provide data once in possession. A1 Fencing - still waiting on RAP process. Saturn still waiting on vegetation management proposals from Horsefield Landscaping. | Saturn (Larry) provided notice via email to GoB on 07/09/21. GoB asked that Saturn submit a signed letter by mail or hand delivery to the GoB referencing the email. Saturn to Inspect on 14/09/21. GoB (Steve) asked that Saturn (Larry) address the outstanding tasks (3) highlighted during site visit on 12/08 and email confirmation completed to GoB. BELCo has switched over to new tansmission cable. BELCo asked to add remote metering monitoring equipment. Saturn (Larry) to follow up with Q-Ship re. Crisson As-Built drawings. GoB (Simon) asked for Saturn to provide data once in possession. A1 Fencing - still waiting on RAP process. Saturn still waiting on vegetation management proposals from Horsefield Landscaping. | Saturn (Larry) provided notice via email to GoB on 07/09/21. Saturn submitted signed letter on 14/09/21 and couriered hard copy to GoB - still not received. GoB (Steve) asked that Saturn (Larry) address the outstanding tasks (3) highlighted during site visit on 12/08 and email confirmation once completed to GoB. BELCo has switched over to new tansmission cable for Project. BELCo asked to add additional remote metering monitoring equipment. Saturn (Larry) to follow up with Q-Ship re. Crisson As-Built drawings week of 20th Sept. GoB (Simon) asked for Saturn to provide data once in possession. A1 Fencing - still waiting on RAP passes. Saturn still waiting on vegetation management proposals from Horsefield Landscaping. | Saturn - IE Intention letter hard copy still not received GoB tracking. Saturn (Larry) to meet with Q-Ship 24/09 re. Crisson As-Built drawings .Saturn to follow up with A1 Fencing to confirm repair schedule. A1 Fencing to clear the 3 meters of vegetation inside the Northern Boundary Fence. | Engineer of Record to extend his letter to include tenant works. Pending test today will able to confirm. Building Permit process complete - all issued to Planning and permit issued. Simon needs comments on the draft lease and Shannon to respond to comments on lease. GIS points from Crisson are still required for under water cable location to complete information for the lease. LH is employing a local diver to gets GPS points, however, no boat was available yesterday but will be early next week dependent on the weather conditions. Q Ship to get GPS points out within 48 hrs of the underwater survey. LH noted that drainage for standing water to take place in place for next 2 weeks. 90% of vegetation has been removed with3 days to complete. A1 Fencing has been unavailable to LH . Minor amount of work. | LH reported that the trench drain to the centre of the site was underway and the vegetation clearing was almost complete. The fence had been cleared on the Finger side to allow access for A1 Fencing to attend the end of the fence. Timing of the work by A1 to be confirmed. It was agreed that the Independent Engineer would issue a complete Practical Completion Statement to capture electrical and also the site issues raised by the Government. The site tide barriers by Saturn with Butterfield will have to be moved for Butterfield to install the Government's boulder barrier to the munitions dock. SC advised that the Gov Engineers have the boulder work in hand with Butterfield but not started yet. | No update | No update | No update | No update | Complete | Complete | Complete | Complete | Complete
27 | 27 | Provide copy of Practical Completion Statement to Government | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we complete work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Gov await Practical Completion Statement when available. | Noted | Noted | Noted | Noted | No Comment | No change | No change | No Update | Noted | No update | Noted | No update | Noted | No update | Noted | Noted | No Update | No Update | No Update | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | Saturn hopeful to have practical completion by end of March | Saturn hopeful to have practical completion by end of March | Saturn hopeful to have practical completion by end of March | Target April 1st. GoB asked that Saturn provide notice if there are any changes to this date. | Target April 1st. GoB asked that Saturn provide notice if there are any changes to this date. | Due to Shelter in Place Order for Island as of 04/04 for two weeks there will be some delays. See Obligation 23 | Island Wide Lock Down extended until May 2nd. See Obligation 23 | Once Lock Down is over, Saturn anticipate it will take two weeks to complete work and do completion inspection. | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | Submarine Cable remediation work - will cause a delay in the issuing of the Practical Completion Statement estimated to be 8-10 weeks. | Practical completion will occur when remediation work on submariune cable completed. | Practical completion will occur when remediation work on submariune cable completed. | Practical completion will occur when remediation work on submariune cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. Saturn to provide latest remediation schedule to GoB which will indicate when final inspection will take place. Practical Completion will occur on that date. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. | Practical completion will occur when remediation work on submarine cable completed. Due to Xmas holidays any review of Practical Completion Statement by GoB may be delayed to week of Jan 4th. 2021 | Practical completion will occur when remediation work on submarine cable completed. Due to Xmas holidays any review of Practical Completion Statement by GoB may be delayed to week of Jan 4th. 2021 | Date of Practical Completion to be confirmed when cable issue resolved. | Date of Practical Completion to be confirmed when cable issue resolved. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | Saturn will coordinate Practical Completion with commissioning process. | No Change until connection issies resolved. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | Saturn - what does the Practical Completion look like? What are GoB expectations/requirements - see Obligation 26 above. Saturn believe may be in position to issue Practical Completion Statement on 21/07/21. | Saturn - what does the Practical Completion look like? What are GoB expectations/requirements - see Obligation 26 above. | Saturn - what does the Practical Completion look like? What are GoB expectations/requirements - see Obligation 26 above. | Saturn - According to DoP (Building Control), interconnection cable report (comms and electrical) results and Independent Engineers (electrical) report will be required for DoP to issue Certificate of Completion and Occupancy (CCO). GoB (Simon) requested that Saturn send CCO to GoB once they receive it. | Saturn - According to DoP (Building Control), interconnection cable report (comms and electrical) results and Independent Engineers (electrical) report will be required for DoP to issue Certificate of Completion and Occupancy (CCO). GoB (Simon) requested that Saturn send CCO to GoB once they receive it. | No Update | No Update | No Update | No Update | GoB (Simon) - Practical Completion Statement document Saturn submitted on 22/09 is not sufficient. GoB (Simon) to send Saturn (Shanna) list of what it needs to contain.GoB (Steve) asked that Saturn (Larry) address the outstanding tasks (3) highlighted during site visit on 12/08 and email confirmation once completed to GoB. | Refer to LH report above. Saturn to provide Pratcical Completion Notice in accord with the Lease Agreement. | No Update | No Update | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete
28 | 28 | Provide Government with 5 working days’ notice of Independent Engineer’s intention to inspect the Tenant’s Works with a view to issuing Notice of Completion of Making Good | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we complete work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn to notify GoB Projet Manager formal written letter (and email). | Noted | Noted | Noted | Noted | Noted | No change | No change | No Update | Noted | No update | Noted | No update | GoB asked for independent surveyors credentials (CV) and contact information which will be shared with relevant GoB Team members. | Mike is waiting on a schedule assurance of availability and will provide information to GoB. | Noted | Mike provided details of the independent engineer in an email on 31 July 2019 | Mike to copy Nana when forwarding a copy to Sudell Joseph | Noted | No Update | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No update | No update | No update | No update | GoB requested all Independent Engineer's Reports be submitted to them as soon as possible. Saturn agree to do so. | Saturn uploaded all Independent Engineer's reports to date to Data Room. | GoB asked that all Independent Engineer's Reports be stamped and signed. | Saturn to follow up with Engineers. | Saturn provided stamped/signed structural report. | Saturn provided stamped/signed structural report. | No update | No update | No update | No update future obligation | No update future obligation | No update future obligation | No update future obligation | Once Lock Down is over, Saturn anticipate it will take two weeks to complete work and do completion inspection. | Once Lock Down is over, Saturn anticipate it will take two weeks to complete work and do completion inspection. | See 26 above. | No update future obligation | Saturn - there be one final inspection meeting with view to issuing practical completion certificate. | No Update | No Update | No Update | No Update | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occurred - coming up against Long Stop Date 30th November need to notify Government if going to miss this date. | Obligation deffered until practical completion has occurred. | Obligation deffered until practical completion has occurred. | Works Long Stop Date extension request. GoB/Saturn agreed that date of extension will be finalised after testing of submarine cable and installation moves forward to gauge timing of finalisation of work on 03/12/20. | Works Long Stop Date extension request. GoB/Saturn agreed that date of extension will be finalised after testing of submarine cable and installation moves forward to gauge timing of finalisation of work on 03/12/20. | Works Long Stop Date extension request. Saturn to provide proposed date to GoB 11/12/20. | Satrun Requested Long Stop date of March 31 2021. GOB to comfirm by letter next week. Saturn will coordinate indenpendent Engineer's Inspection with testing and commissioing. | Saturn Requested Long Stop date of March 31 2021. GOB to confirm this has been approved by Minister week of 18/01/21. Saturn will coordinate indenpendent Engineer's Inspection with testing and commissioing. | Saturn Requested Long Stop date of March 31 2021. GOB to confirm this has been approved by Minister week of 25/01/21. Saturn will coordinate indenpendent Engineer's Inspection with testing and commissioing. | Saturn Requested Long Stop date of March 31 2021. GoB Letter drafted ready for signing. Both parties agreed to defer signing until question of potential delays due to BELCo network upgrades resolved. See Obligation 24. | Saturn Requested Long Stop date be changed from March 31 2021 to April 31st 2021 to account for possible further delays due to proposed BELCo network upgrades. GoB to submit to Minister for signing and provide to Saturn for stakeholders/investors. | Saturn Requested Long Stop date be changed from March 31 2021 to April 30th 2021 to account for possible further delays due to proposed BELCo network upgrades. GoB has submitted change to PS/Minister for signing and provide to Saturn for stakeholders/investors. GoB to follow up with PS/Minister. | Saturn Requested Long Stop date be changed from March 31 2021 to April 30th 2021 to account for possible further delays due to proposed BELCo network upgrades. GoB has submitted change to PS/Minister for signing and provide to Saturn for stakeholders/investors. GoB to follow up with PS/Minister. Saturn had meeting with BELCo re. possible delays due to TDR system upgrades. Uncertain as to requirement/need for upgrades. Discussion with BELCo continues. | GoB (Steve) confirmed Long Stop Date Extension Letter is moving forward should have letter week of 01/03/21. | GoB (Steve) confirmed Long Stop Date Extension Letter is moving forward hoping to have letter week of 08/03/21 to provide to Saturn. | GoB (Steve) confirmed Long Stop Date Extension Letter is moving forward hoping to have letter week of 15/03/21 to provide to Saturn. Saturn asked that date be changed beyond April 30th 2021 considering other delays to project. | GoB asked for Saturn to provide an email emphasising urgency of request and new extension date. | SC reported that the long Stop Date extension letter for June 30th is still with the Minister's Office for signing and will request a response for next week. | SC reported that the PW Minister's Office has referred the letter to the AG Chambers and SC will follow up to see if it can be returned to Saturn next week. | No Update | No Update | No Update | No Update | No Update | GoB's SC reported that the PW Minister's Office has referred the letter to the AG Chambers. Saturn requested meeting with AG Chambers to discuss delay in sign off on Long Stop Extension Letter. | GoB Long Stop Extension Letter signed by Minister. Saturn requested further discussion with GOB (PS) re. changing the actual extension date before agreeing to sign the document. GoB (Steve Conway) to speak with PS to move conversation forward. Saturn to email GoB outlining reasons for request. | No update | GoB (Steve Conway) to provide update re. Saturn request for extension of Long Stop Date to Nov. 15th 2021. | GoB (Steve Conway) to provide update re. Saturn request for extension of Long Stop Date to Nov. 15th 2021. (Current June 30th 2021) by 23/06/21 | GoB (Steve Conway) has suggested a meeting with the PS/Minister to discuss Long Stop Date further week of June 28th 2021. Saturn (Neel) requested an email from GoB that GoB would not call out Saturn for defaulting based on the expiration of the Long Stop Date (June 30th 2021). Saturn suggested that the Lease be executed and held in escrow until commissioning has been completed. Saturn believes Lease already in agreed form. | Minister of Public Works (MPW) has agreed to change the Long Stop Extension Letter Date to Nov. 15th 2021 as requested by Saturn. GoB(Steve) to followup with MPW to get signed Letter and send it to Saturn. | GoB sent signed Long Stop Extension Letter to Saturn on 03/07, Saturn countersigned and returned to GoB on 05/07. | No Update | No Update | No Update | No Update | No Update | No Update | No Update | No Update | GoB requested that Saturn provide copy of Certificate of Completion and Occupancy once received from Department of Planning. | GoB (Planning)requires final certification from Bermuda Fire and Rescue Service (BFRS) Certificate before they could issue Certificate of Completion and Occupancy. Saturn (Larry) working on providing this to GoB(Planning) | Fefer to LH report above | No Update | GoB (Simon) This will be required if IE discovers items which need addressing under the Practical Completion Statement | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete
29 | 29 | Provide copy of Notice of Completion of Making Good to Government | Saturn | Saturn to confirm (after Satisfaction Date) | Will do when we complete work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn to upload Notice of Completion document to Data Room and email GoB Project Manager when this has been done. | Noted | Noted | Noted | Noted | No Comment | No change | No change | No Update | Noted | No update | Noted | No update | Noted | No update | Noted | No update | No update | Noted | Noted | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No Update (future obligation) | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | No update future obligation | See obligation 28 above. | No Update | No Update | No Update | No Update | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation differed until practical completion has occured | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occured | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | No Update | Obligation deffered until practical completion has occurred | No Update | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | No change | No change | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | Obligation deffered until practical completion has occurred | GoB to review Engineer's Report once received and discuss with Saturn. | See 27 Above | Refer to LH report above. | No Update | GoB (Simon) This will be required if IE discovers items which need addressing under the Practical Completion Statement | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete
30 | 30 | Maintenance Schedule | Saturn | Draft to be provided to Government for approval | Will do when we get closer to commercial operations. | Noted | Will do when we get closer to commercial operations. | Noted | Will do when we get closer to commercial operations. | Noted | Will do when we begin work. | Noted | Noted | Will do when we begin work. | Will do when we begin work. | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Noted | Saturn has agreed to supply Schedule when they get closer to start of commercial operations. | Noted | Noted | To be provided in July | Will be tied into the appointment of O&M contractor. | Noted | No change | No change | No Update | Saturn needs to address befor practical completion. Neel and Simon to discuss O&M contract to be signed in August. GoB need to see before signed. | Maintenance schedule discussions to occur in about a month once the O&M contractor is selected. | Noted | No update | Noted | No update | Noted | Will be delivered when Saturn requests approval of O&M contractor | Will be delivered when Saturn requests approval of O&M contractor | Noted | Noted | Saturn - maintenance schedule will be an appendix in the O&M contract. | Saturn - maintenance schedule will be an appendix in the O&M contract. See 13 above. | Saturn - maintenance schedule will be an appendix in the O&M contract. See 13 above. | GoB - received draft O&M contract with Maintenance Schedule in appendix. Will respond with comments. | GoB - received draft O&M contract with Maintenance Schedule in appendix. Will respond with comments. | GoB to review and respond. AM to follow up with GoB Team | GoB has some comments waiting on others before sending to Saturn. | GoB to provide comment by Web Nov. 6th | GoB to provide comment by Wed Nov. 13th | GoB to provide comment by Nov. 15th | GoB reviewing maintenance schedule attached to Noesis sub agreement in the context of tenant's maintenance obligations under the lease. | Saturn to redraft O&M contract and send a copy to GoB by 06/12/19. | Saturn to redraft O&M contract and send a copy to GoB by 06/12/19. | Saturn to redraft O&M contract and send a copy to GoB by 27/12/19. | No update | No update | No update | Outstanding obligation | Saturn's Investors providing further comment as part of O&M Contract. Saturn to share with GoB once they have received these comments. | Saturn's Investors providing further comment as part of O&M Contract. Saturn to share with GoB once they have received these comments. | Saturn Investors still reviewing draft O&M contract | Saturn Investors still reviewing draft O&M contract | Saturn Investors still reviewing draft O&M contract | No update | No update | No update | No update | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | See obligation 13 above. | GoB working on draft version of Maintenance Schedule to be included in the Lease Agreement. GoB stakeholders to review and then it will be shared with Saturn when ready. | GoB produced draft version of Maintenance Schedule to be included in the Lease Agreement. GoB will share with Saturn once complete. | GoB shared draft document with Saturn 11/06 and asked for comment. Once agreed upon will become Schedule 5 of the Lease which is to be granted to Saturn following practical completion. | Saturn review of GoB draft document in progress. | Saturn review of GoB draft document in progress. O/M contractor will also need to review document and provide feedback. | Saturn reviewed no comments. Waiting for O/M contractor to review and provide feedback. | GoB draft Maintence Schedule - Saturn reviewed no comments. Waiting for O/M contractor to be selected for them to review and provide feedback. See Obligation 13 | Saturn - Waiting for O/M contractor to be selected for them to review and provide feedback. See Obligation 13 | Saturn - Waiting for O/M contractor to be selected for them to review and provide feedback. See Obligation 13 | Saturn - Waiting for O/M contractor to be selected for them to review and provide feedback. See Obligation 13 | Saturn - Waiting for O/M contractor contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contractor contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contractor contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contractor t to be finalised. See Obligation 13 | Saturn - Waiting for O/M contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contract to be finalised. See Obligation 13 | Saturn - Waiting for O/M contract to be finalised. See Obligation 13 | See Obligation 13..waiting for app roval of the O&M c | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | See Obligation 13 | Part of BAC Maintenance contract. | Copy to go in data room with O&M Contract | See Obligation 13 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
31 | 31 | Location and width of Easement Strip | Saturn | Details to be provided to Government | Provided drawing but will finalize after construction. | Noted | Provided drawing but will finalize after construction. | Noted | Provided drawing but will finalize after construction. | Government received revised Lease Plan from Saturn on 12/03 . Lease Plan sent to Estates for review. | We await update from Saturn. | Government waiting on Estates to finalise approval of Lease Plan. | Government waiting on Estates to finalise approval of Lease Plan. | Saturn awaits update from Government. | Saturn awaits update from Government. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Saturn to respond to Estates. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Saturn to respond to Estates. | Saturn/DoE and Estates had meeting on 05/04/19 to finalise discussion. Estates sent update to Saturn on 11/04/19. Any update from Saturn? | Saturn is currently reviewing and will provide update shortly. | Saturn is currently reviewing and will provide update shortly. | Saturn is currently reviewing and will provide update shortly. | Please confirm that this was not already addressed in Saturn's proposed revised Planning Application drawings sent to Aran on 02/05/19? | Drawings sent in advance of formal application to expedite process, Director of Planning has no objections, but wants all stakeholders to sign off.Aran will follow up with Minister to obtain sign-off. | GOB requested that Saturn revise the drawings sent to GOB on 02/05/19 to correct errors. Revised drawings sent to GOB. on 08/05/19. GOB to review and respond before Saturn submit to Planning. | Noted | GOB received revised drawing set from Saturn on 15/05/19. Please confirm they have been sent to Estates for review and comment. | As requested Saturn sent revised drawing set to Estates on 17/05/19 | Estates still reviewing drawing set. | Any Update? | Saturn has finalized the language and were updating the drawing sets our amendment to the planning application. | Noted | Noted | Final plans have been submitted to Aran showing final location of access road. | No Update | GoB. to provide final Lease Plan drawings as part of Agreement for Lease amendments. | Simon will send a revised plan from the government which is on a government template with Saturn's plans. | Simon sent latest version of ammendment to Agreement for Lease on 08/07 containing Lease Plan/Site Access Protocol | Will be discussed on call on Monday | This is captured in the latest Lease Plan drawings which will form part of the amended Agreement for Lease document. | Single plan in final form will cover this | Noted | Single plan in final form will cover this | No Update | Noted | Noted | GoB - will be captured in Lease Agreement lease plan. | GoB - will be captured in Lease Agreement lease plan. | GoB - will be captured in Lease Agreement lease plan. | No Update | No Update | No Update - will be captured in Lease Agreement lease plan. | No Update - will be captured in Lease Agreement lease plan. | No Update | No update | No update | GoB asked Saturn to confirm that they are satisfied with the wording of section 3.1 (2) b. | Saturn confirmed verbally that they are satisfied with the wording of section 3.1 (2) b. | Complete | Complete | No update | No update | No update | No update | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
32 | 32 | Building Permit | Government | Awaiting Government Response. | Awaiting Government Response. | We note your comments in the Annual Update in respect of the Building Permit that Saturn is “Awaiting discussion around reasonable fees”. The level of Building Permit fees is a matter of public record and Saturn should have been aware of them when formulating its bid for the Solar Project. Planning fees are not freely negotiable. Whilst Government may be prepared to discuss with Saturn the level of Building Permit fees to be applied to the Solar Project, Saturn’s obligations in respect of the Solar Project are clearly set out in the project documents. | Noted, we will continue to seek further feedback from Jeane. | Noted | We await response from Government. | Noted | Please provide Saturn on any updates to this obligation. | Government is waiting for final decision from the Minister of Finance. | Minister of Finance has approved a fee of $100k. Instruction given to Department of Planning to issue invoice once they are satisfied that all other relevant Plannning Act obligations are met. | Saturn understands that the building permit fees are now: $100,000 USD. | Saturn has received the draft letter regarding building permit fees and is in the process of reviewing. Please provide any further updates. | Minister of Finance has approved a fee of $100k.The Department of Planning has issued the Building Permit Fees Letter to Saturn with payment instuctions (11/04/19). Please confirm when payment has been made. | Building Permit Fees received on 17/04/19. Building Permit Issued on 17/04/19 | Complete | Saturn to call site inspector | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
33 | 33 | Fees | Government | Awaiting Government Response. | Awaiting Government Response. | Planning fees are not freely negotiable. Whilst Government may be prepared to discuss with Saturn the level of Building Permit fees to be applied to the Solar Project, Saturn’s obligations in respect of the Solar Project are clearly set out in the project documents. | Noted, we will continue to seek further feedback from Jeane and Aran. | Noted | We await response from Government. We are available to discuss details with the Minister of Finance to help expediate this critical step in our permitting process. Having made this request in December, 2018, we wish for a response shortly. | Government reminds Saturn that whilst Government may be prepared to discuss with Saturn the level of Building Permit fees to be applied to the Solar Project, Saturn’s obligations in respect of the Solar Project are clearly set out in the project documents. Government is in discussions internally to decide if it reduces the fee and will let Saturn know when it has made a decision. | Please provide Saturn on any updates. | Government is waiting for final decision from the Minister of Finance. | Minister of Finance has approved a fee of $100k. Instruction given to Department of Planning to issue invoice once they are satisfied that all other relevant Plannning Act obligations are met. | Saturn understands that the building permit fees are now: $100,000 USD. | Saturn has received the draft letter regarding building permit fees and is in the process of reviewing. | Minister of Finance has approved a fee of $100k.The Department of Planning has issued the Building Permit Fees Letter to Saturn with payment instuctions (11/04/19). Please confirm when payment has been made. | Building Permit Fees received on 17/04/19. Building Permit Issued on 17/04/19 | Complete | Saturn to call site inspector | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
34 | 34 | Land Lord's Works - Fence | Government | Government started site clearing. Waiting for Performance bond to continue with site clearing | N/A | N/A | N/A | GoB. to meet with Saturn on 07/03/19 Build Team as part of request to change lease plan area. | Saturn has received comments from the Government and is in the process of reviewing. | Government is reviewing as part of the request for change in the lease area which we received from Mike Brugge on 12/03/19. Government will continue site clearing once this process is concluded and the Site bond is in place. | Please provide Saturn on any updates. Saturn has uploaded the lease footprint which shows specifically the interconnection cable location for the easement which will attach to the project land lease. | Government is reviewing as part of the request for change in the lease area which we received from Mike Brugge on 12/03/19. Government will continue site clearing once this process is concluded and the Site bond is in place. | Government will continue site clearing once the Site bond is received and Saturn has submitted the Construction Plan from Saturn to help Government facilitate Tenant's and Landlord's works. | Final Site Bond will be finalized soon and Saturn will provide. In the meantime please provide any updates, if necessary. | Larry to get back to Government. | Government will continue site clearing once the Site bond is received. | GoB. preparing to go out to Tender for Land Lord's Works week of April 22nd. | GoB. published Tender for Land Lord's Works on 22/04/19. Will keep Saturn up to date when appropriate. | GoB. published Tender for Land Lord's Works on 22/04/19 | GOB published Tender for Land Lord's Works on 22/04/19. GOB attempting to expedite this process. | GOB published Tender for Land Lord's Works on 22/04/19. GOB attempting to expedite this process. | The Director of the Department of Energy emailed Larry and Mike on 02/05/19 to clarify Government's intentions in this regard. | GOB is proceeding with their RFQ process. Documents were published April 30. Will keep Saturn abreast of progress. | GOB is proceeding with their RFQ process. Documents were published April 30. Will keep Saturn abreast of progress. | Noted | GoB RFQ process is closed and are reviewing bids. Will notify Saturn when contract has been awarded. | Noted | Noted | Noted | Close to going to cabinet to award contract to contractor, once it is reviewed by the Department of Energy. | Ministry of Public Works to assume responsibility for the fulfillment of this obligation. | Aran is attempting to set up a meetingwith Public Works to begin the handover process | Aran is attempting to set up a meetingwith Public Works to begin the handover process | No Update | Hand Over Process Started from DoE to MPW. | No update regarding GoB appointing a contract. Based on communicatons, Mike was expecting an announcement last Friday. Mike to clarify with Nana, who will in turn, follow up with the Minister of Public Works. Department of Energy has already made their recommendation to Public Works as to who to select as the contractor. | No update | Aran has notified Skyport and Ministry of Public Works. Aran to provide contacts of airport group to Mike so that he can follow up. Mike confirmed with John Pears of Skyport that the fence is a requirement. | Saturn has proposed to take over the contract to build the Fence/Gate. Saturn agreed to make proposal to Minister of Public Works in formal letter. Aran has contacted the relevant Airport stakeholders 20/7/19 to get feedback on proposal to NOT build the fence/gate. | Saturn's proposal is time sensitive and may lapse. Saturn to follow up with Myron on 7/29/19. | Noted | Saturn to prepare the terms in a formal letter to the Minister. Shanna & Mike to work on this the week of August 12. | Mike Brugge issued email to Misister Burch requesting confirmation of Saturn's request on Lift and Shift provision. Minister Burch confirmed the understanding of Senior Crown Counsel. | GoB requested and Saturn provided GoB 23/08/19 the Purchase Order which outlines the scope of work that Staurn have agreed to do to build the fence and gate. | Site orientation with A1 Fencing took place on 28th Aug. They intend to mobilise on 30th Aug. start build Sept. 3rd. and complete build Sept. 13th | Saturn - Build started on Sept. 3rd., posts being put in the ground Sept. 6th and on target to complete build Sept. 13th. Requested someone from Ministry of Public Works attend inspection of work once it is complete with other stakeholders (Skyport). | Saturn - Build substantially complete. Expected completion 17/09/19. MPW Chief Engineer Kirk Outerbridge has been notified and will commit staff to attending inspection. Saturn to confirm with Steve Conway when that will be. | Saturn - Build substantially complete. Delay due to Hurricane Humberto. Hanging Gates and Barbed Wire. Expected completion 27/09/19. Saturn to confirm with Steve Conway when inspection will take place. | Saturn - Build complete. Asked Skyport/ASSI for inspection and sign off. GoB - proposal of installation of additional gate at eastern end to facilitate access for Vegetation Clearing. Saturn raised concern about delay in sign off and question of cost of security to cover build time. GoB - to confirm details of proposal and respond to Saturn. | GoB - posts for additional gate at eastern end have been installed/gate being built and installation will be completed by 14/10/19. Skyport/ASSI inspection week of Oct. 21st | GoB/Saturn - confirm that A1 Fencing has guaranteed to complete build of Eastern Gate by end of day Monday October 21st. Saturn contacted Skyport to confirm new inspection date for week of 11/10/19. | Fence and Gates have been completed and Skyport has assessed. Skyport willing to sign off on but asked that an additional 'span' be built on Western End. Saturn to confirm with A1 Fencing that this can be done and at what cost. Saturn Request for formal acknolwedgment of building of fence/gate. Steve Conway to provide an update on his return to the offce. | Saturn inquiring with A1/Skyport about what additional fencing they require and what can be done based on what those requirements are. | A1 Fencing to contact Skyport directly to confirm its further requirements (if any) regarding the fence. | No update - waiting for A1 Fencing to respond. | No response from A1 Fencing. GoB to follow up with them directly. | A1 Fencing has stated that the additional changed to the design of the Fence requested by Skyport is no longer required. Email sent by GoB to Skyport on 26/11/19 to confirm this and ask them for final sign off. | A1 Fencing has stated that the additional changed to the design of the Fence requested by Skyport is no longer required. Email sent by GoB to Skyport on 26/11/19 to confirm this and ask them for final sign off. | Complete | No update | No update | No update | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| 35 | Land Lord's Works - Site Clearing | Government | Fencing | N/A | N/A | N/A | N/A | Saturn has updated the Government on the status of the fence and security and would like to receive formal approval to proceed with building a fence and finalizing the fees | Government is reviewing as part of the request for change in the lease area which we received from Mike Brugge on 12/03/19. Government will continue site preparation once this process is concluded and the Site bond is in place. | Please provide Saturn on any updates. | Government is reviewing as part of the request for change in the lease area which we received from Mike Brugge on 12/03/19. Government will continue site clearing once this process is concluded and the Site bond is in place. | Government will consider building the Fence as a priority once we receive the Site Bond | Final Site Bond will be finalized soon and Saturn will provide. Please provide updates on Saturn's request re: fencing. | Please provide any update on this item. | Government agreed to prirotise building of Northern Boundary Fence and Saturn agreed to submitting application for build as a revision to their original Planning Application. All relevant information sent to Saturn on 08/04/19. Any update? | Government agreed to prirotise building of Northern Boundary Fence and Saturn agreed to submitting application for build as a revision to their original Planning Application. All relevant information sent to Saturn on 08/04/19. Does Saturn have an update | Government agreed to prirotise building of Northern Boundary Fence and Saturn agreed to submitting application for build as a revision to their original Planning Application. All relevant information sent to Saturn on 08/04/19. Any update from Saturn? | Saturn hoping to submit revised planning application week of April 29th. Saturn to send to Vicki Periera and Aran McKittrick before submitting formally to Planning. | Saturn hoping to submit revised planning application week of April 29th. Saturn to send to Vicki Periera and Aran McKittrick before submitting formally to Planning. | Saturn hoping to submit revised planning application week of April 29th. Saturn to send to Vicki Periera and Aran McKittrick before submitting formally to Planning. | Noted - with thanks to Saturn again for agreeing to include the Fence/Gate application as part of its own Planning Application revision. | Noted | Noted | Larry will take one last look of the drawings (to the submission of the Planning Permission). If the drawings are satisfactory and send them to the Planning Permission. | GOB received revised drawing set from Saturn on 15/05/19. Please confirm they have been sent to Estates for review and comment. | On 5/22 Aran confirmed with Vicki Pereira that until she has received written proof of consent from all of the stakeholders she will not be in a position to sign off on Saturn’s Revised Planning Application. Aran has followed up with Sean and Nana of Estates and they have agreed to review the drawings on 5/22. Aran also emailed Skyport to ask for an update on their request to their regulator (ASSI) to approve the fence and gate and is awaiting feedback from them. Therefore, printing and submission of revised Planning Application is delayed until such time that we have all the responses from stakeholders in hand. | On 5/23 Skyport requested clarification of some information re. fence/gate. GoB Project Manager will respond as soon as possible once the information is made availble to them. | Any Update? | An email chain was sent to Larry regarding stakeholder approvals. Larry included approvals in submission to planning. | Ministry of Public Works to assume responsibility for the fulfillment of this obligation. | Aran is attempting to set up a meetingwith Public Works to begin the handover process | Aran is attempting to set up a meetingwith Public Works to begin the handover process | No Update | Hand Over Process Started from DoE to MPW | Aran to follow up with Skyport and get back to Saturn. | DoE has provided all the contract and contact information to MPW's Bob Lortie for MPW to persue the conversation re. Fence/Gate further. | Minister will hopefully indicate who contractor is by end of day July 12th. | The Site Clearing Project has been delegated to Tina Searle of the Ministry of Public Works - introductry email sent to Saturn on 19/07/19 | Nana to follow up with Tina to see if cabinet approved the contract amount for the cite-clearing contractor who ceased work on 7/24/19. | Noted | Clearing to resume Wednesday August 14 | Clearing did not resume. Saturn issued Indemnity Notice on August 14th. | GoB - No update to provide at this time. Idemnity Notice physically received by AG Chambers 19/08/19 | Saturn - Tina Searle/Nana Turkson/2 members of Butterfield Excavation visited site on Wed. 28th to perform a site assessment. Butterfield being vetted to determine if they can undertake work, vetting process could take 7-10 days according to Tina Searle. | GoB - Myron Simmons is discussing with PS/Minister. Steve Conway to follow up with PS for an update. | GoB - MPW further site visit with contractor on 13/09/19. Steve to provide update from this visit to Saturn. | GoB - Site clearing contract was signed on 25/09/19 with Butterfield Excavation Ltd. Skyport security clearance documents being applied for by Butterfield. | GoB - provided updates in face to face meeting on 02/1019. GoB to provide further updates re. start date of Vegetation Site Clearing as soon as we have them. | GoB - have made efforts to help expedite Skyport security pass application process for Butterfiled Excavation. Saturn Work Schedule being reviewed by GoB and will be discussed asap. | GoB - Police have completed vetting of RAP applications for Butterfield Excavation. Skyport still to complete remainder of application process. Saturn's Larry Henry to meet GoB's - Tina Searle and Butterfield Excavation on-site 23/10/19 go through work plan/site on saftey protocols etc. | Butterfield expected to receive security passes 25/10/19, mobilize on 26/10/19 and start Site Clearing on 28/10/19. | Butterfield mobilised and work commenced on Oct. 28th | Site clearance works were progressing. Saturn pleased with the progress being made by Butterfield. | GoB. hoping to have completed site clearance by Dec. 1st. | Saturn requested clarification of status of site clearing work. Final piles on eastern boundary have been driven and work is due to commence on framing and module mounting. Removal of any additional vegetation will be more difficult once this work begins. | Govt. - Site clearance was completed on 2 December 2019. | Saturn has confirmed that Site Clearing Work has been completed by Butterfield Excavation. | Complete | No update | No update | No update | No Update | Saturn requested support for additional costs. GoB informed Saturn would need to submit these using the relevant formal processes in order for them to consider them. | No Update | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| 36 | Request for Advance Tenant's Works | Saturn | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Saturn requested permissionl to begin certain of the Tenant’s Works prior to practical completion of the Landlord’s Works | Government Requested Constuction Work Plan in order to assess request. | Government waiting on Saturn Work Plan | Saturn finalising Work Plan | Saturn finalising Work Plan | Received the Work Plan from Saturn on 09/04/19. Responded with Advance Tenant's Works Draft Approval Letter on 11/04/19. Waiting on Saturn's response to Letter. | Received the Work Plan from Saturn on 08/04/19. Responded with Advance Tenant's Works Draft Approval Letter on 11/04/19. Waiting on Saturn's response to Letter. | Received the Work Plan from Saturn on 08/04/19. Responded with Advance Tenant's Works Draft Approval Letter on 11/04/19. | Saturn has provided a markup of the draft on 26/04/19. GoB. to review and respond | GOB has confirmed receipt and will review. | Sarurn is currently reviewing internally the amendment to the agreement for lease. | GOB has accepted Saturn's proposed revisions and has submitted them to the Minister of Public Works for his review and approval. | Noted | The Advance Works Consent Letter should be in place before Saturn starts work. GOB has submitted this to the Minister of Public Works for his review and sign off. | Sign off expected by May 13th. | The Advance Works Consent Letter should be in place before Saturn starts work. GOB has submitted this to the Minister of Public Works for his review and sign off. | Aran followed up twice more with the PS Rochester of the Ministry of Public Works to ask him for an update on getting the Minister of Public Works to review and sign the Advance Works Consent Letter. PS Rochester’s response was that the Minister was reviewing the Letter on May 20th. Aran has not had an update despite sending him another follow up email. Minister is aware of Saturn’s construction timeline and the requirement that the Advance Works Consent Letter be signed before any work can commence. | GoB Project Manager working with Estates to finalise language and submit to Minister for his final review and signing | Advance Works Consent Letter issued on 27 May 2019. | Completed | GoB responded to Saturn on 31/05/19 and requested changes to the wording and advising that this Notification should be submitted after Planning Approval has been granted. |  |  | No Update | DoE Received MPW Letter of Advance Works from Saturn. DoE to confirm whether this completes the Obligation? | Saturn sent Letter of Intention to carry out Advance Works and Begin Construction on 09/07/19 | GoB received Saturn Letter of Intention to carry out Advance Works and Begin Construction on 09/07/19 | Letter of Intention to begin work dated June 25th addressed this. Simon to speak to Aran and respond. Simon to ask Shanna to upload into the data room. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| 37 | Request for Acknowledgment of Execution of Project Agreements | Government/Saturn | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Request for permission to Share Project Agreement Documents. | Request for permission to Share Project Agreement Documents. | Project Team have drafted a letter confirming Project Agreements have been executed. Letter submitted to Minister of Home Affairs for review and signature 08/04/19 | Letter of Confirmation of execution of Project Agreements sent to Saturn on 12/04/19 | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| 38 | Letter of no objection to increase land area from 18 acres to 19.05 acres, and change in the location of the easement strip for the transmission line. | Government | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Saturn drafted a request to increase the land size. GoB replied with suggested edits to the request letter. Saturn issued revised letter on 5/30. | Steve Conway from Estates to provide confirmation. The no objection letter and boundaries marked off information anticipated to be completed by Monday. Aran will speak to Sean about pinning boundaries. | This forms part of Saturn's Request for approval from Estates for revised planning application. See row 23. | No objection letter received on 6/14. | No objection letter uploaded into data room. | No Update | The No Objection Letter was received from the Minister of Public Work on 6/14. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| 36 | Hazardous Materials (Fuel Lines) Indemnity Notice/Remediation Plan | Government | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Saturn to provide Field Report/Investigation and Results/Drawing of Fuel Lines and Uploaded to the Data Room | Saturn Provided Field Report/Investigation and Results/Drawing of Fuel Lines and Uploaded to the Data Room. Issued Hazardous Substance/Indemnity Notice 20/09/19. | GoB. reviewing Saturn's Hazardous Substance Notice and proposed Remediation Plan | GoB. will contract Sam Moniz of ATI and GoB. Hazardous Materials team to do remediation work. | 15/10/19 GoB. team pumped out the exposed pipes out of the original 5 locations. Socks/swabs were inserted into the exposed pipe at the 5 locations to soak up any liquid residue. | 23/10/19 GoB. and Sam Moniz of ATI cut and capped the exposed pipes from the 5 locations sufficient to allow Saturn to complete its piling works at these locations. The cut pipes were placed in sealed bags and removed from the Property. | Saturn exposed the pipes in the first valve pit located along the route of the Transmission Line Trench. ATI has tested the fuel pipes in the valve pit for hazardous substances by drilling test holes in them. These fuel pipes were found not to contain any hazardous substance but fumes were detected in them. GoB. intention to allow these fuel pipes to air for 2 to 3 days to allow the fumes to dissipate and then cut and cap the fuel pipes sufficient to allow the Transmission Line Trench to be dug. | Saturn agreed to uncover the remaining pipes so they can be assessed by GoB. Team/ATI week of 11/11/19. | Saturn hope to have the remaining pipes exposed by 20/11/19. GoB. sent Hazardous Substance Notice Response/Remediation Plan on 14/11/19. | Saturn requested that GoB. commence remediation work prior to all pipes being exposed. GoB. will consider and respond. | GoB moving forward with contracting AIS to complete the remediation work. Saturn has uncovered a further two sets of pipes on the western boundary. Saturn to confirm status of remaining trenching work week of Dec. 2nd. Saturn and GoB to continue to work together to move this obligation forward. | GoB moving forward with contracting AIS to complete the remediation work. Govt. will notify Saturn of timeline when it has been finalised. | AIS has started to remove remainder of fuel pipes as part of remedication plan. Saturn has proceeded with laying of cables. | No update | No update | No update | Saturn requested compensation for additional costs. GoB to respond. | GoB to respond to Saturn's request for reimbursement of additional costs as outlined in their original Idemnification Notice. | GoB to provide response week of 27/01/20 | GoB response approved by GoB Senior Counsel 31/01/20. Waiting on Minister to sign and will forward to Saturn. | Saturn Confirmed receipt of GoB response. | Saturn still reviewing GoB response. | Saturn still reviewing GoB response. | Saturn will try and provide a response by week of March 2nd | Saturn will provide a response week of March 9th. | Saturn will provide a response week of March 16th. | Saturn response letter produced waiting on suplementary document to support before sending to GoB Team. | GoB received Saturn response on. GoB Team discussed and will send recommendation to PS/Minister on 27/03 | GoB to follow up with Steve Conway re. PS/Minister of Public Work's response. | GoB to follow up with Steve Conway re. PS/Minister of Public Work's response. | Steve Conway of GoB to follow up with. PS/Minister of Public Work's response by week of 27/04/20. | Steve Conway of GoB to follow up with. PS/Minister of Public Work's response by week of 04/05/20. | Steve Conway of GoB to follow up with. PS/Minister of Public Work's response by week of 11/05/20. | GoB - payment of latest Indemnity Notice request by Saturn has been approved. Saturn to provide wiring information to GoB for payment. | GoB - payment of latest Indemnity Notice request by Saturn has been approved. Saturn has provided invoices and payment information. GoB to confirm when payment has been made. | GoB - payment of latest Indemnity Notice request by Saturn has been approved. Saturn has provided invoices and payment information. GoB to confirm when payment has been made. | GoB to follow up week of 08/06/20. | GoB requested additional company information from Saturn in order to complete payment of hazardous materials cost claim. | Payment Approved and submitted for payment. Expected to clear week of 22/06/20 | Saturn to confirm payment has been received. | Saturn to confirm payment has been received. | Saturn to confirm payment has been received. GoB to do the same. | GoB - delay in payment. Resubmitted payment will update when have more information re. wiring details. | GoB - delay in payment. Resubmitted payment will update Saturn when have more information re. wiring details. | Saturn - Payment has been received. | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete | Complete
| 30 | Proposed Sale of Leasehold | No Update |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Saturn Update on Sale of Project to Bermuda Infrastructure Fund - LOI signed, negotations continue, no defenitive agreement executed. | Saturn Update on Sale of Project to Bermuda Infrastructure Fund - LOI signed, negotations continue, no defenitive agreement executed. | LOI still in effect - discussions still hapenning not in a position to move to a definitive agreement. | LOI still in effect - discussions still hapenning not in a position to move to a definitive agreement. | LOI still in effect - discussions still hapenning not in a position to move to a definitive agreement. | LOI still in effect - discussions still hapenning not in a position to move to a definitive agreement. | Saturn to send GoB request to receive 3rd party change of control. GoB (Simon) to discuss with GoB Team before providing feedback to this request. | Sale of Project to 3rd Party - GoB (Simon) to send Saturn (Shanna/Stephen) what is required under Schedule 2 of the Lease before GoB can approve. | Propsed sale of leasehold details to be confirmed when required under Schedule 2 and will be released when ready. | No Update | No Update | Saturn working through Consent Requirements of Sect. 114B License, consulting stakeholders (BELCo/RA). Had call with RA - they stated new owners would have to apply for new Bulk Generation License - which could take up to3 months to complete. | No Update | No Update | Saturn working through Consent Requirements of Sect. 114B License, consulting stakeholders (BELCo/RA). Had call with RA - they stated new owners would have to apply for new Bulk Generation License - which could take up to 3 months to complete. | New Purchaser submitted change of control consent request to the RAB, 60 -90 day time frame for completion. | No Update | No Update | No Update - Saturn waiting for RA response to Change of Control Consent Request application
| 31 | Site Access Protocol/Lease | GOB |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | (GoB) Aran to package the points on the note from Ari Ming to develop the Site Security Protocol. SC to follow up Aran. Simon will assist. | GoB (Simon) will draft the proposed site access protocol for next week. | GoB (Simon) sent to Saturn on Oct. 15th for feedback/comment. | Larry (Saturn) to provide more detailed comment/suggestions by 25th Oct. | GOB (Simon) to finalise and send to Skyport/BAA after getting confirmation from Skyport (Shanna) they had no further comments/changes on 29/10/21. | GoB (Simon) comments sent and received from Skyport/BAA 03/11. GoB (Simon) to finalise relevant version of Site Access Protocol share with (Saturn/BAA) and include it in Lease once approved by all. | SAP - GoB (Simon) to send clean copies to all stakeholders, revised version to be placed in the Lease. LEASE - GoB (Simon) to send Saturn Final Plan, Saturn to approve asap. Simon to create engrossments of Lease and send to Minister of Public Works and Saturn (Directors) to sign in order to execute by 16/11/21. Simon will create closing statement re.lease payment. | Lease rental payments - GoB (Steve) to provide point of contact details to Saturn (Steve) re. invoicing etc. GoB (Simon) - Lease executed 17/11. Confirmation sent to BELCo to satisfy requirements under PPA. BELCo are satisfied that these have been met. GOB obligations under the Lease Agreement completed - GoB moved to a landlord status. Saturn will now need to report annually under Implementation Agreement - i.e. milestones which have occurred under PPA, any other material changes/authorisations made under the Implementation Agreement etc. etc. | GoB (Simon) - Saturn's couriered signed Lease documents yet to be received. Will continue to track and notify Saturn once received. GoB (Steve) - lease payment account setup . Saturn (Steve) to email GoB (Steve/Kofi) once initial payment has been made. | Saturn (Steve) - communication and process re.monthly lease payments now in place. From January payments will be made prior to 1st of month. GoB (Simon) received - wet inkied copied of the Lease. Corresponding copies will be sent back to Saturn for their records. To submit to Tax Commisioner to ensure exemption from Stamp Duty. | GOB (Simon) - where should he send counter part to Lease Agreement. Saturn (Shanna) - will confirm. GoB(Aran) - asked Shanna to respond to email re. status/role of Saturn Bermuda subsidaries created under 114B license. GoB (Simon) Lease agreement exempt from Stamp Duty has been confirmed by Tax Commissioner. Saturn (Steve) lease payment for January 2022 created ready for payment.
| 32 | Security access | Saturn |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | LH reported that he was dealing with a security issue at the time of the meeting. SkyPort had today closed the access across the Airport airside to the Finger because of invalid vehicle standards being used by the security contractor. The Saturn security contractor is the same contrractor used by SkyPort. It is understood that the security contractor was short of vehicles and used one for Saturn access without proper stickers etc. LH was resolving this at the time of the meeting. Site access protocols should have a statement to agreee that Skyport can't deny access to the Finger and cannot issue instructions to vacate the site. There was discussion that access could be by boat outside of control of Skyport. If contractors get second level of training with AVOP then access should not be an issue with Skyport. Simon advised it would be useful to agree water access points on the Finger and agree them with Skyport and BAA. Notice can still be given to Skyport for boat access. It was noted that the Finger is private Government land out of the jurisdiction of Skyport. LH will report on status later today. | GoB (Aran) suggested standardising penalties for breaking Site Access Protocol need to discussed and agreed with Skyport considering issue with AVOP passes week of Oct. 1st. | No Update | No Update | No Update | Complete | Complete | Complete | Complete | Complete
| 33 | PR Related to Completion of Project | Saturn/GoB |  | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | N/A | Shanna to ask Saturn CEO Doug Wagner whether Saturn want to do Press Release/Statement/Conference re. completing of Project. | Saturn (Neel) would be willing to participate in PR to mark completion of project if desired by GoB. | To Take Plave after Nov. 12th. Saturn commited to attending in person to do ribbon cutting etc. GoB (Aran) to organise format/timing etc. with GoB/Saturn/Skyport/BAA/BELCO (Fabian) etc. | Saturn -want to have firm COD date agreed before commit to a specific Press Conference date. Commited to attending in person to do ribbon cutting etc. GoB (Aran) to organise format/timing etc. with GoB/Saturn/Skyport/BAA/BELCO (Fabian) | Saturn - want to have firm COD date agreed before commit to a specific Press Conference date. Commited to attending in person to do ribbon cutting etc. GoB (Aran) to facilitate planning between GoB/Saturn. | GoB (Aran) facilitating organisation of Media Release/Ribbon Cutting with Saturn (Devin) and DCI. Saturn's (Ray Roth's) availability sent to DCI. Date between Dec. 6th - 8th requested by GoB. | GoB (Aran) - has decided to not move forward with Ribbon Cutting/Media Release at this time. GoB support Saturn in moving forward with own Media Release. Saturn (Neel) - Saturn to do Media Release will contact GOB (DCI) comms team accordingly. | GoB (Aran) - no comment from GoB on Saturn's Media Release. GoB resoncsidering own Press Release. Saturn (Neel) - waiting for sign off from relevant parties before moving forward with distributing Saturn's Media Rlease. | GoB (Aran) - both GoB and Saturn communications teams have prepared own Media/Press Releases. GoB still considering holding Press Conference. Will inform Saturn if they decide to proceed.
The Government of Bermuda and Saturn Solar Bermuda 1 Ltd. Bermuda Solar Project Checklist
December 14th 2021
BELCO - The Bermuda Electric Light Co. Ltd.
GoB- The Government of Bermuda
Saturn - Saturn Solar Bermuda 1 Ltd
RA - The Regulatory Authority of Bermuda
MPW - Ministry of Public Works
Note on AQ8: Steven Farrugia: Keep line item open until effective date is confirmed
Note on AQ11: Steven Farrugia: Keep line item open until Effective Date is confirmed.